## Perspectives
PID | Description | Progress
1 | Financial & Growth | 0
2 | Customer | 0
3 | Employee | 0

## Initiatives
PID | INID | Description | Progress | notes
1 | 1 | Operational Efficiency | 0
1 | 2 | Identify Growth Areas | 0
1 | 3 | Improve Freight Position | 0
1 | 4 | Software Utilization | 0
2 | 1 | Enhance Brokerage Strategy | 0
2 | 2 | Enhance Customer Experience | 0
2 | 3 | Maximize Sales Performance | 0
2 | 4 | Target Farmers of the Future | 0
2 | 5 | Develop Commerical Origination Strategies | 0
2 | 6 | Develop Direct Shipment Business | 0
3 | 1 | Employee Development | 0
3 | 2 | Support Employee Wellness | 0
3 | 3 | Improve Communication | 0
3 | 4 | Enhancement of Training Program | 0
3 | 5 | Employee Engagement | 0
-

## Actions
PID | INID | ACTID | Description | Champion | Team | Due Date | Progress | Notes
1 | 1 | 1 | Develop a process to improve efficiencies of the harvest delivery trucking program | Taylor | Kali, Devin | 2017-05-01 | 0
1 | 1 | 2 | Regenerate awareness to Patron Access functionality and offerings | Dusty | Quentin, Nichole | 2017-06-01 | 0
1 | 1 | 3 | Create inventory sheet consistency b/w members | Lance | Operations Team | 2017-02-28 | 0
1 | 1 | 4 | Explore electronic settlements and transfers with end users | Kali | Ted, Tricia | 2018-02-01 | 0
1 | 1 | 5 | Review TMA revenue agreement on an annual basis | Ted | Danny, CEOs | 2017-06-01 | 0
1 | 1 | 6 | Investigate need for minimum bushel amounts on purchase contracts | Kali | Tricia, Devin, Grain Cooridinators | 2017-06-01 | 0
1 | 1 | 7 | Research need for signatures on Sales & Purchase contracts | Devin | Kali, Lance | 2017-06-01 | 0
1 | 1 | 8 | Conduct drier efficiency study for TMA locations | Lance | Ted, Operations Group | 2017-09-01 | 0
1 | 2 | 1 | Develop a strategy around partnering w/or acquiring books of crop insurance business | Scotty | Devin, Connor | 2018-02-01 | 0
1 | 2 | 2 | Create asset plans for specialty grains | Ted | Lance | 2017-09-01 | 0
1 | 2 | 3 | Develop an operational and marketing strategy for handling canola | Ted | Todd, Lance, Devin | 2017-05-01 | 0
1 | 2 | 4 | Identify future franchasing and partnership opportunities | Ted | Devin | 2018-02-01 | 0
1 | 2 | 5 | Explore combining grain & private crop insurance programs | Nick | Westin, Justin, Todd | 2017-08-01 | 0
1 | 3 | 1 | Create freight variance report | Lance | Taylor, John | 2017-03-01 | 0
1 | 3 | 2 | Do a feasiblity study on fleet ownership | Ted | Operations Group | 2017-12-01 | 0
1 | 3 | 3 | Prepare for FSMA regulations regarding traceablity efforts | Ted | Operations Group | 2018-01-01 | 0
1 | 3 | 4 | Study single dispatch approach and potential efficiencies | Ted | John, Taylor | 2017-06-01 | 0
1 | 4 | 1 | Evaluate grain accounting software & producer risk management programs | Devin | Kali, Cory, Dusty, Jordan, Tricia | 2017-06-01 | 0
2 | 1 | 1 | Reasearch marketplace and area competition | Mike | Devin | 2017-01-31 | 0 | Identified rates and requirements for local brokerage companies. Scheduled on site collaboration meeting with similar brokerage company.
2 | 1 | 2 | Develop a business and marketing plan | Mike | Devin | 2017-03-01 | 0 | Basic outline created.
2 | 1 | 3 | Complete licensing process to be an IB | Mike, Devin |  | 2017-03-01 | 0 | Testing materials have been ordered and schedule set for January and February studying.
2 | 1 | 4 | Enhance existing livestock risk management programs | Scotty | Devin, Mike | 2017-03-01 | 0 | Trained staff and held customer meetings on LRP & PRF policies. Identifing existing livestock producers in territory.
2 | 2 | 1 | Investigate intent & best approach to customer surveys | Jordan | Todd, Weston, Cole | 2017-09-01 | 0
2 | 2 | 2 | Each division will conduct meetings with top 15 accounts annually | Devin | Scotty | 2017-12-01 | 0
2 | 2 | 3 | Test and develop a call forwarding system | Devin | Dusty, Kali, Matt | 2017-09-01 | 0
2 | 2 | 4 | Create a social media strategy to communicate brand story | Jess | Justin, Nichole, Scotty | 2017-06-01 | 0
2 | 2 | 5 | Develop a vendor scorecard to evaluate key vendors in each division | Ted | Lance, Devin | 2017-12-01 | 0
2 | 2 | 6 | Research and implement the use of electronic warehouse receipts for producers | Debi | Kali, Tricia | 2017-06-01 | 0
2 | 3 | 1 | Grow share of wallet with fifty 2000 acre producers | Devin | Scotty | 2018-01-01 | 0
2 | 3 | 2 | Develop a share of wallet report for local grain delivery and crop insurance customers | Nick | Devin | 2017-09-01 | 0
2 | 4 | 1 | Create a task force to plan and execute relevant producer meetings | Dusty | Jess, Weston, Justin, Cory | 2017-12-01 | 0
2 | 4 | 2 | Identify strategic producers of the future for each region of our territory | Devin | Nick, Jordan, Scotty | 2017-06-01 | 0
2 | 5 | 1 | Identify commerical growth opportunities based off analysis of CoBank project | Ted | Cole, Lance | 2017-06-01 | 0
2 | 6 | 1 | Identify potential process efficiencies throughout the entire direct shipment process | Cory | Kali, Alex, Debi, Taylor, Lance | 2017-05-01 | 0
3 | 1 | 1 | Develop personal development plans for each employee | Devin | Scotty, Ted, Lance | 2017-12-01 | 0
3 | 1 | 2 | Create internal training pathways and tracking methods | Devin | Dusty, Scotty | 2017-06-01 | 0
3 | 1 | 3 | Develop simulated training scenarios | Scotty | Todd, Weston | 2017-12-01 | 0
3 | 1 | 4 | Each division will visit a similar division of another company | Ted | Devin, Scotty | 2018-01-01 | 0
3 | 2 | 1 | Greater than 50% participation in the company wellness program | Ted | Devin, Kali | 2018-01-01 | 0
3 | 2 | 2 | Identify ways to improve the quality of life for all employees | Devin | Tricia, Lance, Kali | 2018-01-01 | 0
3 | 2 | 3 | Investigate outside the box merchandising and accounting labor structures | Tricia | Ted, Kali, Lance | 2018-01-01 | 0
3 | 3 | 1 | Develop an Ag in the classroom presentation | Quentin | Justin, Connor, Nichole | 2017-09-01 | 0
3 | 3 | 2 | Hold informational TMA 101 meetings for new and existing employees | Ted, Devin | Kali, Lance | 2017-08-01 | 0
3 | 3 | 3 | Hold one joint meeting for full board of owners | Ted, Devin | Kali, Lance | 2017-05-01 | 0
3 | 4 | 1 | Identify the training needs of TMA employees | Devin | Scotty | 2017-03-01 | 0
3 | 4 | 2 | Develop an onboarding process for all grain employees for member cooperatives | Devin | Kali, Lance | 2017-05-01 | 0
3 | 5 | 1 | Breakout employee survey results by division | Devin | Ted | 2018-03-01 | 0
3 | 5 | 2 | Host family appreciation day | Devin | Ted, Scotty | 2017-09-01 | 0

## Tasks
PID | INID | ACTID | TASKID | Description | Due Date | Weight | Complete | Measure
1 | 1 | 1 | 1 |  |  | 3 |  | 0
1 | 1 | 1 | 2 |  |  | 3.5 |  | 0
1 | 1 | 1 | 3 |  |  | 3.5 |  | 0
1 | 1 | 2 | 1 |  |  | 3 |  | 0
1 | 1 | 2 | 2 |  |  | 3.5 |  | 0
1 | 1 | 2 | 3 |  |  | 3.5 |  | 0
1 | 1 | 3 | 1 |  |  | 3 |  | 0
1 | 1 | 3 | 2 |  |  | 3.5 |  | 0
1 | 1 | 3 | 3 |  |  | 3.5 |  | 0
1 | 1 | 4 | 1 |  |  | 3 |  | 0
1 | 1 | 4 | 2 |  |  | 3.5 |  | 0
1 | 1 | 4 | 3 |  |  | 3.5 |  | 0
1 | 1 | 5 | 1 |  |  | 3 |  | 0
1 | 1 | 5 | 2 |  |  | 3.5 |  | 0
1 | 1 | 5 | 3 |  |  | 3.5 |  | 0
1 | 1 | 6 | 1 |  |  | 3 |  | 0
1 | 1 | 6 | 2 |  |  | 3.5 |  | 0
1 | 1 | 6 | 3 |  |  | 3.5 |  | 0
1 | 1 | 7 | 1 |  |  | 3 |  | 0
1 | 1 | 7 | 2 |  |  | 3.5 |  | 0
1 | 1 | 7 | 3 |  |  | 3.5 |  | 0
1 | 1 | 8 | 1 |  |  | 3 |  | 0
1 | 1 | 8 | 2 |  |  | 3.5 |  | 0
1 | 1 | 8 | 3 |  |  | 3.5 |  | 0
1 | 2 | 1 | 1 |  |  | 3 |  | 0
1 | 2 | 1 | 2 |  |  | 3.5 |  | 0
1 | 2 | 1 | 3 |  |  | 3.5 |  | 0
1 | 2 | 2 | 1 |  |  | 3 |  | 0
1 | 2 | 2 | 2 |  |  | 3.5 |  | 0
1 | 2 | 2 | 3 |  |  | 3.5 |  | 0
1 | 2 | 3 | 1 |  |  | 3 |  | 0
1 | 2 | 3 | 2 |  |  | 3.5 |  | 0
1 | 2 | 3 | 3 |  |  | 3.5 |  | 0
1 | 2 | 4 | 1 |  |  | 3 |  | 0
1 | 2 | 4 | 2 |  |  | 3.5 |  | 0
1 | 2 | 4 | 3 |  |  | 3.5 |  | 0
1 | 2 | 5 | 1 |  |  | 3 |  | 0
1 | 2 | 5 | 2 |  |  | 3.5 |  | 0
1 | 2 | 5 | 3 |  |  | 3.5 |  | 0
1 | 3 | 1 | 1 |  |  | 3 |  | 0
1 | 3 | 1 | 2 |  |  | 3.5 |  | 0
1 | 3 | 1 | 3 |  |  | 3.5 |  | 0
1 | 3 | 2 | 1 |  |  | 3 |  | 0
1 | 3 | 2 | 2 |  |  | 3.5 |  | 0
1 | 3 | 2 | 3 |  |  | 3.5 |  | 0
1 | 4 | 3 | 1 |  |  | 3 |  | 0
1 | 4 | 3 | 2 |  |  | 3.5 |  | 0
1 | 4 | 3 | 3 |  |  | 3.5 |  | 0
1 | 4 | 4 | 1 |  |  | 3 |  | 0
1 | 4 | 4 | 2 |  |  | 3.5 |  | 0
1 | 4 | 4 | 3 |  |  | 3.5 |  | 0
1 | 5 | 1 | 1 |  |  | 3 |  | 0
1 | 5 | 1 | 2 |  |  | 3.5 |  | 0
1 | 5 | 1 | 3 |  |  | 3.5 |  | 0
2 | 1 | 1 | 1 |  |  | 3 |  | 0
2 | 1 | 1 | 2 |  |  | 3.5 |  | 0
2 | 1 | 1 | 3 |  |  | 3.5 |  | 0
2 | 1 | 2 | 1 |  |  | 3 |  | 0
2 | 1 | 2 | 2 |  |  | 3.5 |  | 0
2 | 1 | 2 | 3 |  |  | 3.5 |  | 0
2 | 1 | 3 | 1 |  |  | 3 |  | 0
2 | 1 | 3 | 2 |  |  | 3.5 |  | 0
2 | 1 | 3 | 3 |  |  | 3.5 |  | 0
2 | 1 | 4 | 1 |  |  | 3 |  | 0
2 | 1 | 4 | 2 |  |  | 3.5 |  | 0
2 | 1 | 4 | 3 |  |  | 3.5 |  | 0
2 | 2 | 1 | 1 |  |  | 3 |  | 0
2 | 2 | 1 | 2 |  |  | 3.5 |  | 0
2 | 2 | 1 | 3 |  |  | 3.5 |  | 0
2 | 2 | 2 | 1 |  |  | 3 |  | 0
2 | 2 | 2 | 2 |  |  | 3.5 |  | 0
2 | 2 | 2 | 3 |  |  | 3.5 |  | 0
2 | 2 | 3 | 1 |  |  | 3 |  | 0
2 | 2 | 3 | 2 |  |  | 3.5 |  | 0
2 | 2 | 3 | 3 |  |  | 3.5 |  | 0
2 | 2 | 4 | 1 |  |  | 3 |  | 0
2 | 2 | 4 | 2 |  |  | 3.5 |  | 0
2 | 2 | 4 | 3 |  |  | 3.5 |  | 0
2 | 2 | 5 | 1 |  |  | 3 |  | 0
2 | 2 | 5 | 2 |  |  | 3.5 |  | 0
2 | 2 | 5 | 3 |  |  | 3.5 |  | 0
2 | 2 | 6 | 1 |  |  | 3 |  | 0
2 | 2 | 6 | 2 |  |  | 3.5 |  | 0
2 | 2 | 6 | 3 |  |  | 3.5 |  | 0
2 | 3 | 1 | 1 |  |  | 3 |  | 0
2 | 3 | 1 | 2 |  |  | 3.5 |  | 0
2 | 3 | 1 | 3 |  |  | 3.5 |  | 0
2 | 3 | 2 | 1 |  |  | 3 |  | 0
2 | 3 | 2 | 2 |  |  | 3.5 |  | 0
2 | 3 | 2 | 3 |  |  | 3.5 |  | 0
2 | 4 | 1 | 1 |  |  | 3 |  | 0
2 | 4 | 1 | 2 |  |  | 3.5 |  | 0
2 | 4 | 1 | 3 |  |  | 3.5 |  | 0
2 | 4 | 2 | 1 |  |  | 3 |  | 0
2 | 4 | 2 | 2 |  |  | 3.5 |  | 0
2 | 4 | 2 | 3 |  |  | 3.5 |  | 0
2 | 5 | 1 | 1 |  |  | 3 |  | 0
2 | 5 | 1 | 2 |  |  | 3.5 |  | 0
2 | 5 | 1 | 3 |  |  | 3.5 |  | 0
2 | 6 | 1 | 1 |  |  | 3 |  | 0
2 | 6 | 1 | 2 |  |  | 3.5 |  | 0
2 | 6 | 1 | 3 |  |  | 3.5 |  | 0
3 | 1 | 1 | 1 |  |  | 3 |  | 0
3 | 1 | 1 | 2 |  |  | 3.5 |  | 0
3 | 1 | 1 | 3 |  |  | 3.5 |  | 0
3 | 1 | 2 | 1 |  |  | 3 |  | 0
3 | 1 | 2 | 2 |  |  | 3.5 |  | 0
3 | 1 | 2 | 3 |  |  | 3.5 |  | 0
3 | 1 | 3 | 1 |  |  | 3 |  | 0
3 | 1 | 3 | 2 |  |  | 3.5 |  | 0
3 | 1 | 3 | 3 |  |  | 3.5 |  | 0
3 | 1 | 4 | 1 |  |  | 3 |  | 0
3 | 1 | 4 | 2 |  |  | 3.5 |  | 0
3 | 1 | 4 | 3 |  |  | 3.5 |  | 0
3 | 2 | 1 | 1 |  |  | 3 |  | 0
3 | 2 | 1 | 2 |  |  | 3.5 |  | 0
3 | 2 | 1 | 3 |  |  | 3.5 |  | 0
3 | 2 | 2 | 1 |  |  | 3 |  | 0
3 | 2 | 2 | 2 |  |  | 3.5 |  | 0
3 | 2 | 2 | 3 |  |  | 3.5 |  | 0
3 | 2 | 3 | 1 |  |  | 3 |  | 0
3 | 2 | 3 | 2 |  |  | 3.5 |  | 0
3 | 2 | 3 | 3 |  |  | 3.5 |  | 0
3 | 3 | 1 | 1 |  |  | 3 |  | 0
3 | 3 | 1 | 2 |  |  | 3.5 |  | 0
3 | 3 | 1 | 3 |  |  | 3.5 |  | 0
3 | 3 | 2 | 1 |  |  | 3 |  | 0
3 | 3 | 2 | 2 |  |  | 3.5 |  | 0
3 | 3 | 2 | 3 |  |  | 3.5 |  | 0
3 | 3 | 3 | 1 |  |  | 3 |  | 0
3 | 3 | 3 | 2 |  |  | 3.5 |  | 0
3 | 3 | 3 | 3 |  |  | 3.5 |  | 0
3 | 4 | 1 | 1 |  |  | 3 |  | 0
3 | 4 | 1 | 2 |  |  | 3.5 |  | 0
3 | 4 | 1 | 3 |  |  | 3.5 |  | 0
3 | 4 | 2 | 1 |  |  | 3 |  | 0
3 | 4 | 2 | 2 |  |  | 3.5 |  | 0
3 | 4 | 2 | 3 |  |  | 3.5 |  | 0
3 | 5 | 1 | 1 |  |  | 3 |  | 0
3 | 5 | 1 | 2 |  |  | 3.5 |  | 0
3 | 5 | 1 | 3 |  |  | 3.5 |  | 0
3 | 5 | 2 | 1 |  |  | 3 |  | 0
3 | 5 | 2 | 2 |  |  | 3.5 |  | 0
3 | 5 | 2 | 3 |  |  | 3.5 |  | 0