## Sales
InitiativeNo | InitiativeDesc | Complete
1 | Maximize sales performance | 50

## Experience Actions
Action No | Action | Progress | Champion | Team | Low | High
1 | Meeting with Land O’Lakes to define MKC needs for customer portal | 20 | Matt | Dave S., Devin, Nichole, Willie, and Kent | 30 | 60
2 | Phase I Completion – Main current MKC website replacement | 30 | Matt | Dave S., Devin, Nichole, Willie and Kent | 30 | 60
3 | Investigate online membership application, credit app, new customer packet, etc. | 50 | Matt | Matt | 30 | 60
4 | Implement annual customer experience face-to-face reviews with targeted accounts | 40 | Willie | Kent, Devin, Dave S. | 30 | 60
5 | Identify methodology to measure customer experience | 10 | Nichole | Devin, Willie, Kent, MKC Way | 30 | 60
6 | Establish YouTube video and hold training sessions for basic navigation of existing customer portal. | 15 | Nichole | Brett, Steve, Erik, Darin | 30 | 60
7 | Continue SOP development, maintenance and management of the process | 70 | Nichole | SOP Committee | 30 | 60
8 | Roll out changes to customer pre-pay input contracts | 75 | Danny | Willie, Kent, Dave S., Dave S. | 30 | 60

## Sales Actions
Action No | Action | Progress | Champion | Team | Low | High
1 | Refine forecasting process to measure variances and tie to incentive | 20 | Kent | Dave S. and Willie | 30 | 60
2 | Hire Master Agronomy Advisor | 50 | Dave S. | Dave S. | 30 | 60
3 | Develop a marketing campaign for CFA with a goal of 75 new loans | 45 | Dave S. | Nichole, Kent, Tim B. | 30 | 60
4 | Incorporate CRM functionality to highlight priority accounts | 75 | Kent | Devin, Matt | 30 | 60
5 | Identify and launch strategy to capture 15 new, $1 millon, combined business unit accounts | 20 | Dave S. | Willie, Kent, Devin | 30 | 60

## Target Actions
Action No | Action | Progress | Champion | Team | Low | High
1 | Sales training to include multi-generational selling | 20 | Willie | Devin, Kent | 30 | 60
2 | Invite 4 growers from targeted geography to Emerging Producers Program with follow-up discussions after | 30 | Willie | Nichole, Devin, Kent | 30 | 60
3 | Build benchmarks from focus group and create SOPs | 50 | Willie | Dave S., Kent, Devin, Erik | 30 | 60
4 | Develop metrics to measure success of Emerging Producers Program through CRM | 40 | Kent | Nichole, Willie, Devin, Kent | 30 | 60

## Precision Actions
Action No | Action | Progress | Champion | Team | Low | High
1 | Improve website content | 20 | Ross | Craig, Dave S., Nichole | 30 | 60
2 | Investigate potential services from UAV licensing | 30 | Ross | Craig, Dave S., GPPA | 30 | 60
3 | Conduct 6-8 precision ag educational meetings with customers | 50 | Ross | Craig | 30 | 60

## Financial Targets
Target No | Target Desc
1 | Grow units by 15% annually
2 | 5% average annualized (over 3 years) external growth
3 | Minimum 2.00% ROS
4 | Meet or exceed the individual location financial plans

## Customer Targets
Column1 | Target Desc
25 | Retain 95% of targeted accounts
25 | 60% share of wallet with targeted accounts
25 | Minimum 15 new customers each year who have $1M combined business potential
25 | Measure customer satisfaction

## Customer Measures
Weight | Measure Desc
40 | Execute a strategic/large customer strategy
25 | Enhance the customer experience
35 | Ease of doing business

## Experience
InitiativeNo | InitiativeDesc | Complete
2 | Enhance customer experience | 20

## Target
InitiativeNo | InitiativeDesc | Complete
3 | Develop strategies to target under 40 | 70

## Precision
InitiativeNo | InitiativeDesc | Complete
4 | Enhance precision ag strategy | 80