## Perspectives
PID | Description | Progress
1 | Financial & Growth | 55.2083
2 | Customer | 41.8542
3 | Employee | 61.45
4 | Organizational Renewal | 51.875

## Initiatives
PID | INID | Description | Progress | Notes
1 | 1 | Identify key market growth areas | 100 | A potential merger partner list with contacts and notes is reviewed and updated every 2 weeks by Darin. (Attach example?) Prospective partnerships with independent retailers are also logged and updated here. The large project list has been updated and prioritized for 2016/17 and is now scheduled to be reviewed quarterly to capture changes and additions in real time. (Attach example?) An alert has been established to revisit the identification of potential green field sites every 6 months with Dave C. and Ted.
1 | 2 | Expense management | 25 | A financial dashboard is currently being created to house location specific sales and expense items by month for key employees to be able to review monthly. IT is troubleshooting the source and flow of data to ensure accuracy and timeliness. Still on pace for a February roll out. Training piece will follow on how to navigate and evaluate the content. *Consider adding an action for monthly variance reporting to encourage usage, understanding, accountability and to measure baseline performance standards. The Margin/Expense Management Committee is established and currently prioritizing cost saving projects, (Attach example?), and finding ways to measure success of each one including BuyPoint which is still in the feasibility phase.
1 | 3 | Board Initiative - Explore criteria for voting membership | 17.5 | Other methods have been identified to compare and contrast. No changes are currently being made but next steps have been identified for preparedness including feasibility reporting to the BOD, reviewing bylaws, and meeting with governance committee for in-depth evaluation.
1 | 4 | Telling the MKC story to merger candidates' board members and employees | 78.3333 | New talking points were created when designing the Initiative In Review for Telling the MKC Story. (Attach example?) Dave C. reviewed these talking points in the November 2015 Monthly Manager Meeting. These talking points were included in December's Team Meeting Agenda to review with entire employee group. A Board Committee has been identified to champion merger candidate meetings & presentations. BOD development sessions are scheduled in Jan & Mar of 2016 to keep momentum in continuing education. *Consider adding new action to include customer testimonial videos.
2 | 1 | Maximize sales performance | 57 | Share of wallet continues to drive sales efforts. Measurements have been established as: 60% + share of wallet per business unit = existing customer, 21%-59% = targeted customer and > 20% = prospective customer. A better & more accurate forecasting tool is up for discussion in Q1 in order to tie to incentive plans appropriately. 2 MAA's have been hired. *Consider adding new actions here regarding MAA smart goals and define 3MIL account strategy. The execution of the CFA marketing plan was proven successful by exceeding the original goal by 48 loans. This is a 46% increase over LY. We are currently testing CRM's capability in generating a priority account report every Monday that pulls accounts that have exceeded their departmentally determined, acceptable length of time without contact. Should go live in FEB. The strategy to capture 15 new 1MIL accounts is underway and on pace with 60 identified targets (Attach list?). Checkpoints are scheduled in Q2 to narrow the focus and discuss capture strategy. War boards, (Attach example?), have been implemented to track and identify Field Marketer goals and pace to goals for inputs and application each month.
2 | 2 | Enhance customer experience | 45 | Relationship with LOL was leveraged to create and successfully launch the new MKC website on January 14th 2016. (Attach link?) Phase one is complete with continued troubleshooting behind the scenes to include enhancements such as depth of organization with employee bios highlighting the youth and expertise of our leadership group. Phase two will include customer log in components, membership materials and career page enhancements. *Consider adding new action items after receiving phase 2 milestones from LOL. Please note, the YouTube videos to assist in navigating the customer portal will be recorded after phase two to capture most current functionality. In reference to implementing customer face to face reviews, it has been determined to utilize CRM's Power Survey module to house the survey questions. Power Survey will be tested on the employee group first before rolling out to customers. An April deadline has been defined to have administered a survey to at least the top 10 accounts. Survey questions (Attach questions?) will be customized for Agronomy services, Grain services, and Energy Services. All of which will be launched strategically by season. Agronomy after fall harvest and Grain after wheat harvest. Energy TBD. Power Survey will also be used to measure specific customer experiences after services or loan fulfillments. It has been determined that customer engagement can be measured by 3 things: 60% share of wallet, 20% service surveys, and 20% of meeting or event attendance currently being tracked by Power Zap Event via CRM. Regarding SOP development, all recorded processes have been transferred to the new template via summer interns (Attach SOP template?). *Consider new action item to audit department files to identify any critical procedures without a formal SOP. Lastly, regarding customer prepay contracts; seed and chemical contracts are done. Fertilizer will not change and Energy is underway but stalled for now. *Consider new action to include formal training and/or checkpoints to determine if new contracts are working as planned.
2 | 3 | Develop strategies to target gaining business with farmers under 40 years old | 53.75 | Sales training to include multigenerational selling techniques will be included in the FLM+ training series. As soon as this piece is incorporated into the curriculum, we will determine how to measure its effectiveness. Generational speaker Bruce Talgan is scheduled for employee groups in January. A special list of invitees was compiled to target Sumner County young producers to attend EPP. Individual follow up calls to these participants is underway. Written survey and instant click survey results have been complied and reviewed by champion group. We are still in the discovery phase for building appropriate benchmarks for farmers under 40. FBN software is still being considered.
2 | 4 | Enhance precision ag strategy | 11.6667 | New website content is live and very well represented. We are still in the approval process with the FAA for our UAV but are currently compiling a list of prospective services to add to our precision ag portfolio upon this approval. Customer education meetings are being planned now for 2016. *Consider new actions to include defining new marketing strategies to drive precision ag services and how this will affect the new sales incentive.
3 | 1 | Communicate the strategic plan to employee group & incorporate into their performance plan | 100 | We are currently showcasing one initiative in review (Attach example?) each month in the monthly manager's meeting consisting of a brief presentation from the champion on how to carry the message over into location team meetings as outlined in the new company wide agenda. (Attach example?) We are leveraging the outreach of the employee newsletter as well and including an initiative article in each edition, relative to what was reviewed that month in their team meetings. (Attach example?). Each review is housed in the M-drive for access and reference when discussing performance plans to determine which initiative or action may resonate with that employee for future mentoring. VIP Meetings have been introduced will occur annually. *Consider adding an action to dive deeper into the employee group with the assistance of VIPs to administer location level strategic planning.
3 | 2 | Living the Four Keys: Safety, Courtesy, Image and Innovation | 71.25 | Safety messages are distributed every Monday by a Safety Committee member. Prescription eye protection, Driver training, and Hot work permits have all been successfully implemented. A more consistent platform for daily safety meetings is currently in review. Location safety audits are underway for 2016 with a goal to have all of them complete by Q2. Accidents are being investigated as they happen and information is being shared at the start of every meeting. *Consider adding an action relative to the proposal for a safety data warehouse. Courtesy tactics currently in place include the monthly customer service topic as well as the incorporation of the 4 keys in the company wide agenda for each location's monthly team meeting. The image audit template has been redesigned and the SOP is in place. Audits are currently underway by the MKC Way Committee. Innovative solutions are being recognized in monthly manager meetings. The MKC Way Committee has created a checklist to monitor submissions and ensure follow through. Standards for incentives are being written now.
3 | 3 | Employee engagement | 65 | The OT & Wage Study are complete with no indication that our ratios and averages are anywhere outside the competitive set. Financial performance standards have been determined for each location and will roll into the new incentive program as scheduled. The Employee Engagement Survey (EES) is scheduled for 2016 and with those results a YOY comparison will determine targets for the 2017 strategic plan with emphasis on employee development and communications. Advertisements for drivers have been posted at local retirement communities to increase peak time workforce needs as well as tapping into other cooperatives' workforces that are on opposite seasons. The Expense/Margin Management Committee conducted a cost analysis on temp/PT vs. FT employees and found favorable results toward FT employment. H-2A Visas have been investigated as well and found to be an undesirable source for seasonal help. Sub surveys will launch after the EES to analyze employee's ideas on quality of life. Geographically selected employee focus groups will also be assembled to gain understanding and create action items toward improvement in Q2.
3 | 4 | Employee development | 36 | Applicator training checklist is developed and currently being revised to accommodate soft skills and 30-60-90 day checkpoints. *Consider adding action to create the SOP and roll out company wide. HPE metrics have been defined and a panel review will be scheduled to discuss HPEs on the list. The first pass on an IDP template was released for review in January. *Consider new actions to drive training to LMs on how to administer IDPs and mentor HPEs. Flyers are being designed to recruit teachers to include instructions on how and where to distribute these flyers. Recruiting efforts for Cloud County program are complete and FLM+ Sales training is underway.
3 | 5 | Drive employee wellness | 35 | *Consider adding new actions to drive the examination of the wellness requirements for the new benefits package.
4 | 1 | Evaluate logistics effectiveness/efficiency | 55 | Proformas and feasibility reports for outright fleet ownership are complete. Meetings are scheduled to occur in Q1 2016 to conduct comparative analysis and determine the best course of action. Razor tracking is fully implemented. *Consider adding new actions that investigate complete functionality.
4 | 2 | Continue to identify software platform enhancements | 85 | A Manager of Applications Development was hired in June 2016. The decision to move forward with Logi has led IT toward more rapid completion of critical dashboards including this one. (Attach project list?)
4 | 3 | Establish education and control measures for grain handling employees | 50 | The scorecard template is complete (Attach example?). Grain quality grades have been determined. Waiting on financial dashboards for locations to examine results and apply to new incentive program.
4 | 4 | Analyze feed operations to optimize performance | 17.5 | Options have been identified for more review.

## Actions
PID | INID | ACTID | Description | Champion | Team | Due Date | Progress
1 | 1 | 1 | Continue discussion with potential cooperative merger partners | Darin | Dave & Senior Leadership Team | ongoing | 100
1 | 1 | 2 | Evaluate existing property upgrades to drive market growth | Jon | Darin, Erik, Steve, Dave S. | ongoing | 100
1 | 1 | 3 | Identify locations for potential greenfield sites | Dave | Ted | ongoing | 100
1 | 1 | 4 | Investigate M&A or partnerships with independent retailers | Dave | Darin, Erik, Steve, Dave S. | ongoing | 100
1 | 2 | 1 | Training on Expense Management Initiatives for key employees | Vice Presidents of Operations | Vice Presidents of Operations | 2016-02-01 | 0
1 | 2 | 2 | Investigate the value of total margin/expense management | Chris | John | 2017-02-01 | 50
1 | 3 | 1 | Investigate other methods | Dave |  | 2016-02-01 | 35
1 | 3 | 2 | Review bylaws for feasibility | Dave |  | 2016-02-01 | 0
1 | 4 | 1 | Provide talking points and other materials to be used in education and relationship-building meetings | Nichole | Executive Team, Communications | 2015-12-01 | 65
1 | 4 | 2 | Provide Board Members development opportunities to educate candidates' Board Members | Dave | Nichole | 2016-02-01 | 70
1 | 4 | 3 | Develop a Board Committee that is responsible for meetings, presentations and education of merger candidates' board members | Dave | Board of Directors | 2016-02-01 | 100
2 | 1 | 1 | Refine forecasting process to measure variances and tie to incentive | Kent | Dave S., Willie | 2016-09-01 | 0
2 | 1 | 2 | Hire Master Agronomy Advisor | Dave S. |  | ongoing | 100
2 | 1 | 3 | Develop a marketing campaign for CFA with a goal of 75 new loans | Dave S. | Nichole, Kent, Tim B. | 2016-02-01 | 100
2 | 1 | 4 | Incorporate CRM functionality to highlight priority accounts | Kent | Devin, Matt | 2015-12-01 | 50
2 | 1 | 5 | Identify and launch strategy to capture 15 new, $1 million, combined business unit accounts | Dave S. | Willie, Kent, Devin | 2016-09-01 | 35
2 | 2 | 1 | Meeting with Land O'Lakes to define MKC needs for customer portal | Matt | Dave S., Devin, Nichole, Willie, Kent | 2015-09-01 | 100
2 | 2 | 2 | Phase I Completion - Main current MKC website replacement | Matt | Dave S., Devin, Nichole, Willie, Kent | 2016-03-01 | 25
2 | 2 | 3 | Investigate online membership application, credit app, new customer packet, etc. | Matt |  | 2015-11-01 | 0
2 | 2 | 4 | Implement annual customer experience face-to-face reviews with targeted accounts | Willie | Kent, Devin, Dave S. | 2016-12-01 | 0
2 | 2 | 5 | Identify methodology to measure customer experience | Nichole | Devin, Willie, Kent, MKC Wat | 2015-12-01 | 65
2 | 2 | 6 | Establish youTube video and hold training sessions for basic navigation of existing customer portal | Nichole | Brett, Steve, Erik, Darin | 2015-11-01 | 50
2 | 2 | 7 | Continue SOP development, maintenance and management of the process | Nichole | SOP Committee | 2016-01-01 | 70
2 | 2 | 8 | Roll out changes to customer pre-pay input contracts | Danny | Willie, Kent, Dave S., Dave S. | 2015-10-15 | 50
2 | 3 | 1 | Sales training to include multi-generational selling | Willie | Devin, Kent | ongoing | 50
2 | 3 | 2 | Invite 4 growers from targeted geography to Emergin Producers Program with follow-up discussions afterward | Willie | Nichole, Devin, Kent | ongoing | 75
2 | 3 | 3 | Build Benchmarks from focus group and create S.O.P.s | Willie | Dave S., Kent, Devin, Erik | 2015-12-01 | 65
2 | 3 | 4 | Develop metrics to measure success of Emerging Producers Program through CRM | Kent | Nichole, Willie, Devin | 2016-05-01 | 25
2 | 4 | 1 | Improve website content | Ross | Craig, Dave S., Nichole | 2016-03-01 | 35
2 | 4 | 2 | Investigate potential services from UAV licensing | Ross | Craig, Dave S., GPPA | 2016-09-01 | 0
2 | 4 | 3 | Conduct 6-8 precision ag educational meetings with customers | Ross | Craig | 2016-03-01 | 0
3 | 1 | 1 | Vice Presidents and Division Managers to overview outcomes of strategic planning twice per year | Amy | VPs, DMs | ongoing | 100
3 | 1 | 2 | Create a company-wide monthly agenda for what will be communicated | Amy | Executive Team, Communications | ongoing | 100
3 | 1 | 3 | Utilize other communication methods to carry message (employee newsletter, employee portal, meeting notes, monthly employee meetings) | Amy | Kerry, Matt, Location Managers | ongoing | 100
3 | 2 | 1 | Task Safety Committee to develop methods to lower Workman's Comp rate to 0.80% or less | Jeff | Safety Committee | annually | 60
3 | 2 | 2 | Design motivational tactics to encourage courtesy |  | MKC Way Committee | 2016-02-01 | 100
3 | 2 | 3 | Continue the image audits |  | MKC Way Committee | 2016-02-01 | 100
3 | 2 | 4 | Celebrate innovation solutions awards |  | MKC Way Committee | 2016-02-01 | 25
3 | 3 | 1 | Conduct an overtime/wages study | Brett | Jeff | 2015-09-01 | 100
3 | 3 | 2 | Set standards per location to be rolled into the new incentive program | Danny | Erik, Steve, Darin, Dave S. | 2016-02-01 | 50
3 | 3 | 3 | Develop hard targets for development and communication using the engagement survey results | Brett | Jeff | 2016-02-01 | 70
3 | 3 | 4 | Investigate opportunites to improve peak-time workforce needs | Brett | Jeff | 2016-02-01 | 55
3 | 3 | 5 | Investigate opportunities to measure employee quality of life | Brett | Jeff | 2016-02-01 | 50
3 | 4 | 1 | Develop Applicator Training | Brett |  | 2016-02-01 | 50
3 | 4 | 2 | Utilize metrics to define HPE's and conduct panel review with executive team | Brett | Sr Mgmt | 2015-09-01 | 25
3 | 4 | 3 | Design PDPs for high potential employees | Brett | Jeff, Sr Mgmt | 2016-02-01 | 35
3 | 4 | 4 | Increase bench-strength and develop pool of seasonal part-time help | Jeff | Brett, Steve, Erik, Darin | 2016-02-01 | 35
3 | 4 | 5 | Create a management development program | Brett |  | 2016-02-01 | 35
3 | 5 | 1 | Investigate potential wellness providers | Hillary | Wellness Committee | 2016-05-01 | 35
4 | 1 | 1 | Continue to investigate fleet ownership feasibility versus the lease/hire option | Erik | Steve, Dave Sell, Doug, John W., Ted | ongoing | 40
4 | 1 | 2 | Compile optimal usage and functionality of Razor Tracking | Erik | Matt, Steve, Dave Sell, Doug, John W., Ted | tied to 411 | 70
4 | 2 | 1 | Hire a Manager of Applications Development | Matt | Matt | 2015-09-15 | 100
4 | 2 | 2 | Identify and complete remaining Business Intelligence and Dashboards | Matt | Danny, Tricia | ongoing | 70
4 | 3 | 1 | Incorporate managers'/superintendents' scorecard into incentive program | Brett | Steve, Erik, Jeff, Darin | 2016-02-01 | 50
4 | 4 | 1 | Explore various Feed operations structures | Dave | Erik, Darin, Steve | 2016-02-01 | 35
4 | 4 | 2 | Develop a plan to present to the Board of Directors | Dave | Erik, Darin, Steve | 2016-02-01 | 0

## Tasks
PID | INID | ACTID | TASKID | Description | Due Date | Weight | Complete | Measure | Notes
1 | 1 | 1 | 1 | Create spreadsheet with all active & prospective discussions | 2015-10-05 | 5 | 1 | 5 | Spreadsheet is created and maintained by Darin.
1 | 1 | 1 | 2 | Email spreadsheet to Darin 2 times a month to update and file | 2015-10-31 | 5 | 1 | 5 | Alerts to Amy are set for every other Monday to obtain updates from Darin.
1 | 1 | 2 | 1 | Update large project list | 2015-11-11 | 5 | 1 | 5 | Jon Brown completed the 2015 updates in December with the assistance of Chris Roberts.
1 | 1 | 2 | 2 | Revisit after staff meetings every other month | 2015-12-15 | 5 | 1 | 5 | Alerts to Amy are set for every other Month to have VPs revisit after staff to keep current.
1 | 1 | 3 | 1 | Identify 5-6 targets | 2015-08-25 | 5 | 1 | 5 | Dave C. keeps target list.
1 | 1 | 3 | 2 | Send email alert to check progress on each every 6 months | 2015-12-15 | 5 | 1 | 5 | Alerts are set to Amy for every 6 months to update targets with Dave C. and Ted.
1 | 1 | 4 | 1 | Add prospective independent retailers to merger discussion spreadsheet | 2015-10-08 | 5 | 1 | 5 | Suggested retailers have been added to the spreadsheet although no progress is logged.
1 | 1 | 4 | 2 | Email spreadsheet to Darin 2 times a month to update and file | 2015-12-15 | 5 | 1 | 5 | Alerts to Amy are set for every other Monday to obtain updates from Darin.
1 | 2 | 1 | 1 | Create location specific financial reports (or use current ones) | 2015-12-14 | 3.5 | 0 | 0 | Dashboard is still being built out. Review meeting is scheduled for wk of Jan 18.
1 | 2 | 1 | 2 | Set meeting to discuss critical expense items to include on training checklist | 2016-01-20 | 3.5 | 0 | 0 | Training will include access to the dashboard and how to interpret the data.
1 | 2 | 1 | 3 | Finalize training checklist and present in monthly manager meeting | 2016-02-24 | 3 | 0 | 0 | Still planning on formal roll out in February. Should consider monthly variance reporting.
1 | 2 | 2 | 1 | Create Committee | 2015-06-11 | 2.5 | 1 | 2.5 | Margin/Expense Management Committee is created.
1 | 2 | 2 | 2 | Prepare list of savings projects and prioritize by most $ saved | 2015-11-01 | 2.5 | 1 | 2.5 | List is made & prioritizing is in progress. Buypoint is still in feasibility phase.
1 | 2 | 2 | 3 | Find ways to measure success of each project | 2015-12-31 | 2.5 | 0 | 0
1 | 2 | 2 | 4 | Define projects for FY 2016 and timeline them | 2016-03-01 | 2.5 | 0 | 0
1 | 3 | 1 | 1 | Set reminder email for Dave end of Q4 2015 | 2015-10-23 | 3.5 | 1 | 3.5 | Alerts to Amy for every quarter to visit with Dave C. about voting membership.
1 | 3 | 1 | 2 | Identify 2 other methods to compare to and draw up SWOTs | 2016-01-08 | 3.5 | 0 | 0 | Will wait for instruction after strategic planning on Jan. 26-28.
1 | 3 | 1 | 3 | Present results of feasability in BOD meeting | 2016-02-18 | 3 | 0 | 0
1 | 3 | 2 | 1 | Arrange meeting with Danny to review bylaws | 2016-02-05 | 3.5 | 0 | 0
1 | 3 | 2 | 2 | Arrange meeting with Governance Committee to review bylaws | 2016-01-30 | 3.5 | 0 | 0
1 | 3 | 2 | 3 | Prepare report for BOD meeting | 2016-02-11 | 3 | 0 | 0
1 | 4 | 1 | 1 | Locate talking points developed for Puerto Rico meeting | 2015-10-30 | 3.5 | 0 | 0 | Cannot be located. Create new list.
1 | 4 | 1 | 2 | Create talking points for employees to use moving forward | 2015-11-01 | 3.5 | 1 | 3.5 | Talking points are highlighted in the "Inititiative in Review" for Telling the MKC Story.
1 | 4 | 1 | 3 | Present in monthly manager meeting to review in team meetings | 2015-12-01 | 3 | 1 | 3 | Complete. Reviewed by Dave C. in November 2015 Monthly Manager Meeting. Consider Customer Testimonal Videos next.
1 | 4 | 2 | 1 | Explore board of directors development programs | 2015-10-01 | 3.5 | 1 | 3.5 | Complete. CHS has opportunities and Chris Fischer is booked for March.
1 | 4 | 2 | 2 | Confirm date and time for training session | 2015-10-15 | 3.5 | 1 | 3.5 | Complete. Development sessions are on the books for February and March of 2016.
1 | 4 | 2 | 3 | Survey BOD for feedback on the session | 2016-01-14 | 3 | 0 | 0
1 | 4 | 3 | 1 | Discuss forming a committee with BOD | 2015-09-01 | 3.5 | 1 | 3.5 | Dave confirms complete.
1 | 4 | 3 | 2 | Consider adding the responsibility to an existing BOD committee or develop all members | 2015-10-01 | 3.5 | 1 | 3.5 | Dave confirms complete.
1 | 4 | 3 | 3 | Make a decision | 2016-02-01 | 3 | 1 | 3 | Dave confirms complete.
2 | 1 | 1 | 1 | Discuss the methodology to forecast properly | 2016-02-01 | 3 | 0 | 0
2 | 1 | 1 | 2 | Build a better forecasting tool | 2016-04-01 | 3.5 | 0 | 0
2 | 1 | 1 | 3 | Tie it to incentive plan | 2016-09-01 | 3.5 | 0 | 0
2 | 1 | 2 | 1 | Hire Master Agronomy Advisor | 2015-11-30 | 10 | 1 | 10 | Hired 2. Next steps include MAA action items & timelining them. Consider 3-3MIL accounts as discussed in VIP.
2 | 1 | 3 | 1 | Push out CFA Postcards | 2015-10-30 | 2.5 | 1 | 2.5 | Postcards were sent.
2 | 1 | 3 | 2 | Create a target list and present to Dave Spears | 2015-11-30 | 2.5 | 1 | 2.5 | List was completed.
2 | 1 | 3 | 3 | Complete all 1 on 1 visits with Field Marketers | 2015-12-31 | 2.5 | 1 | 2.5 | Tim met with each Field Marketer.
2 | 1 | 3 | 4 | Progress report on all new CFA loans to Dave Spears | 2016-01-30 | 2.5 | 1 | 2.5 | 123 loans captured exceeding the 75 goal. This is a 46% increase over LY.
2 | 1 | 4 | 1 | Sign integration agreement with PowerObjects | 2015-11-01 | 2.5 | 1 | 2.5 | Signed.
2 | 1 | 4 | 2 | Define acceptable length of days with no contact | 2015-11-15 | 2.5 | 1 | 2.5 | 21 days defined for agronomy. Other departments will determine their own.
2 | 1 | 4 | 3 | Create alerts to push out every Monday to Field Marketers | 2015-12-10 | 2.5 | 0 | 0 | Testing is being completed now by Devin and Kent.
2 | 1 | 4 | 4 | Create report to send out to Managers once a month | 2015-12-30 | 2.5 | 0 | 0
2 | 1 | 5 | 1 | Willie and Kent provide Dave Spears a list of targeted growth accounts | 2015-12-01 | 3.5 | 1 | 3.5 | List compiled by obtaining 3-6 accounts from each Field Marketer. 60 identified.
2 | 1 | 5 | 2 | Willie and Kent checkpoint with Dave Spears | 2016-04-30 | 3 | 0 | 0
2 | 1 | 5 | 3 | Willie and Kent continue go to market strategy | 2016-08-31 | 3.5 | 0 | 0
2 | 2 | 1 | 1 | Invite LOL to Groveland for a meeting | 2015-08-28 | 5 | 1 | 5 | Complete.
2 | 2 | 1 | 2 | Follow up with LOL and receive milestone timeline | 2015-09-30 | 5 | 1 | 5 | Timeline received and launch milestone fullfilled.
2 | 2 | 2 | 1 | Redesigned website | 2016-01-14 | 2.5 | 1 | 2.5 | Complete.
2 | 2 | 2 | 2 | Redesigned customer portal | 2016-01-14 | 3.5 | 0 | 0
2 | 2 | 2 | 3 | Redesigned careers | 2016-01-14 | 4 | 0 | 0
2 | 2 | 3 | 1 | Investigation | 2016-09-15 | 10 | 0 | 0
2 | 2 | 4 | 1 | Choose method to administer review; possibly CRM | 2015-11-01 | 2.5 | 0 | 0 | CRM Power Survey Plus functionality not tested yet. If not CRM then Field Marketers will collect data manually.
2 | 2 | 4 | 2 | Come up with 7 universal questions | 2015-12-15 | 2.5 | 0 | 0 | Questions are being revised from open ended to quantifiable.
2 | 2 | 4 | 3 | Define accounts and schedule reviews | 2016-01-30 | 2.5 | 0 | 0 | Goal is to have top 10 done by April 1, 2016.
2 | 2 | 4 | 4 | Collect data and create action plans for Field Marketers | 2016-03-30 | 2.5 | 0 | 0
2 | 2 | 5 | 1 | Investigate CRM capabilities | 2015-11-01 | 3.5 | 0 | 0 | Investigation is complete. Will use CRM Power Survey Plus but still need to test funtionality on employee group first.
2 | 2 | 5 | 2 | Define measures of engagement | 2015-11-15 | 3 | 1 | 3 | 60% share of wallet, 20% service surveys, 20% meeting attendance.
2 | 2 | 5 | 3 | Have a survey meeting to define types and targets | 2015-11-20 | 3.5 | 1 | 3.5 | Meeting held and survey types defined. Schedule another meeting to reconfirm types and questions for each to pass forward to Dustin.
2 | 2 | 6 | 1 | Meet with IT to understand portal modules | 2015-10-10 | 2.5 | 1 | 2.5 | Meeting held and modules defined.
2 | 2 | 6 | 2 | Map and script the content | 2015-10-30 | 2.5 | 1 | 2.5 | Script is complete.
2 | 2 | 6 | 3 | Troubleshoot the flow | 2015-11-30 | 2.5 | 0 | 0 | Will need to revisit once new site is launched.
2 | 2 | 6 | 4 | Record final version and set up training schedule | 2015-12-30 | 2.5 | 0 | 0
2 | 2 | 7 | 1 | Create SOP Committee and choose SOP template | 2015-01-30 | 3.5 | 1 | 3.5 | Complete.
2 | 2 | 7 | 2 | Begin process transfers into new template | 2015-02-01 | 3.5 | 1 | 3.5 | Interns completing transfers.
2 | 2 | 7 | 3 | Continue to transfer processes; last count 106 | 2015-11-30 | 3 | 0 | 0 | All transfers are complete. SOP template is now used for all new processes. Committee will internally audit any processes w/o an SOP.
2 | 2 | 8 | 1 | Decide upon 4 new types of pre-pay contracts | 2015-08-10 | 1 | 1 | 1 | Decisions have been made.
2 | 2 | 8 | 2 | Go through due diligence for each one | 2015-09-30 | 2 | 1 | 2 | Complete.
2 | 2 | 8 | 3 | Have seed & fertilizer contracts complete | 2015-10-15 | 1 | 0 | 0 | Seed is done. Fertilizer is not.
2 | 2 | 8 | 4 | Have energy and CP contracts complete | 2015-12-15 | 2 | 1 | 2 | Chemical is done. Check on Energy.
2 | 2 | 8 | 5 | Lawyer assessments and approvals for all contracts | 2015-12-30 | 2 | 0 | 0
2 | 2 | 8 | 6 | Formal training for key employees on all contracts | 2016-01-30 | 2 | 0 | 0
2 | 3 | 1 | 1 | Determine source and curriculum for training | 2015-09-01 | 2.5 | 1 | 2.5 | Will be administered as a topic in the FLM+ curriculum. Verify in syllabus.
2 | 3 | 1 | 2 | Acquire training schedule through FLM+ | 2015-10-01 | 2.5 | 0 | 0
2 | 3 | 1 | 3 | Discuss effectiveness of administration of topic | 2015-12-30 | 2.5 | 0 | 0
2 | 3 | 1 | 4 | Consider guest speakers to enhance effectiveness | 2016-01-15 | 2.5 | 1 | 2.5 | Bruce Tulgan scheduled in February.
2 | 3 | 2 | 1 | Compile list of invitees to include Sumner County | 2015-11-15 | 2.5 | 1 | 2.5 | Complete.
2 | 3 | 2 | 2 | Send out invitations | 2015-11-30 | 2.5 | 1 | 2.5 | Complete.
2 | 3 | 2 | 3 | Ensure Field Marketers made invitational follow up calls | 2015-12-01 | 2.5 | 1 | 2.5 | Complete.
2 | 3 | 2 | 4 | Set up internal meeting to discuss info collected from follow up | 2016-01-29 | 2.5 | 0 | 0 | Willie is calling on each Sumner Co. invitee personally. Will set up meeting afterward.
2 | 3 | 3 | 1 | Consider FBN software | 2015-11-01 | 3 | 1 | 3 | Back to discovery phase.
2 | 3 | 3 | 2 | Run a pilot on a few producers and collect data | 2015-12-15 | 3.5 | 1 | 3.5 | Farmers Bureau Network software may not be best course of action.
2 | 3 | 3 | 3 | Set up a meeting to discuss results and how to move forward | 2015-12-30 | 3.5 | 0 | 0 | Conference call scheduled for 1/19.
2 | 3 | 4 | 1 | Create survey questions to launch after EPP | 2016-01-10 | 2.5 | 1 | 2.5 | Power Survey not ready to launch. Used written survey and instant click survey methods.
2 | 3 | 4 | 2 | Launch through CRM | 2016-01-22 | 2.5 | 0 | 0 | Maybe next year.
2 | 3 | 4 | 3 | Discuss results and log changes for next year | 2016-03-01 | 2.5 | 0 | 0
2 | 3 | 4 | 4 | Begin planning EPP 2017 | 2016-05-01 | 2.5 | 0 | 0
2 | 4 | 1 | 1 | Provide LOL current precision ag data for Phase 1 | 2015-09-30 | 3.5 | 1 | 3.5 | Completed in Phase 1.
2 | 4 | 1 | 2 | Continue to collect new content & ideas to prepare for updates | 2016-02-15 | 3.5 | 0 | 0
2 | 4 | 1 | 3 | Evaluate new website and update as necessary | 2016-03-30 | 3 | 0 | 0
2 | 4 | 2 | 1 | Obtain UAV licensing | 2016-01-30 | 3 | 0 | 0
2 | 4 | 2 | 2 | Make a list of services offered or intended to offer | 2016-02-28 | 3.5 | 0 | 0
2 | 4 | 2 | 3 | Discuss marketing options for selected UAV services | 2016-04-01 | 3.5 | 0 | 0
2 | 4 | 3 | 1 | Prepare a schedule with dates, times & locations for new year | 2015-12-05 | 3 | 0 | 0 | Ross confirms in progress.
2 | 4 | 3 | 2 | Discuss marketing collateral needs and timelines | 2015-12-30 | 3.5 | 0 | 0 | There is a new sales incentive to to drive precision ag services. Find out what marketing channels are being used and what collateral is needed.
2 | 4 | 3 | 3 | Collect information from customers & discuss results in Monthly Managers meetings | 2016-03-30 | 3.5 | 0 | 0
3 | 1 | 1 | 1 | Schedule dates for planning sessions (Aug & Jan) | 2015-06-01 | 3.5 | 1 | 3.5 | Complete.
3 | 1 | 1 | 2 | Schedule date for recap @ monthly manager meeting (March) | 2015-09-01 | 3.5 | 1 | 3.5 | Complete. Tuesday March 15, 2016.
3 | 1 | 1 | 3 | Schedule date for VIP meeting (Dec) | 2015-11-11 | 3 | 1 | 3 | Complete. December 21-22, 2015.
3 | 1 | 2 | 1 | Create a schedule & review template for each initiative to cover 1 in every monthly manager's meeting | 2015-08-30 | 3.5 | 1 | 3.5 | Complete. 2016 Calendar complete. Template complete.
3 | 1 | 2 | 2 | Create universal team meeting agenda template to include above intiatives in review | 2015-09-30 | 3.5 | 1 | 3.5 | Complete and offically rolled out in October 2015.
3 | 1 | 2 | 3 | Create a synopsis of each initiative including interactive talking points | 2015-12-30 | 3 | 1 | 3 | Complete and part of Amy's monthly tasks.
3 | 1 | 3 | 1 | Publish a newsletter article relative to the initiatives in review monthly | 2015-12-30 | 2.5 | 1 | 2.5 | Complete and part of Amy's monthly tasks.
3 | 1 | 3 | 2 | Put initiatives in review on M-Drive for all user access | 2015-12-30 | 2.5 | 1 | 2.5 | Complete and part of Amy's monthly tasks.
3 | 1 | 3 | 3 | Visit 3-4 team meetings/month to ensure consistency | 2015-12-30 | 2.5 | 1 | 2.5 | Complete and part of Amy's monthly tasks. This includes Sales/Ops meetings as well.
3 | 1 | 3 | 4 | Ensure Champions are prepared to present intiatives in review at monthly manager's meetings | 2015-12-30 | 2.5 | 1 | 2.5 | Complete. Champions and Executive Team review and approve each initiative before monthly manager meeting.
3 | 2 | 1 | 1 | Create weekly safety messages and distribute every Monday | 2015-02-01 | 1 | 1 | 1 | Complete and part of Safety Committee's responsibilies.
3 | 2 | 1 | 2 | Create SOP for prescription eye protection | 2015-04-30 | 1 | 1 | 1 | Complete and rolled out in Sept 2015.
3 | 2 | 1 | 3 | Implement driver training program | 2015-06-30 | 2 | 1 | 2 | Complete.
3 | 2 | 1 | 4 | Revise the hot work permit SOP | 2015-04-30 | 2 | 1 | 2 | Complete.
3 | 2 | 1 | 5 | Create consistent platform for tailgate safety talks | 2016-03-01 | 2 | 0 | 0 | Template currently in review.
3 | 2 | 1 | 6 | Perform location safety audits | 2016-06-30 | 2 | 0 | 0
3 | 2 | 2 | 1 | Create monthly customer service topic for review in team meetings | 2015-12-01 | 10 | 1 | 10 | Created by MKC Way Committee each month.
3 | 2 | 3 | 1 | Redesign image audit template | 2015-08-01 | 3.5 | 1 | 3.5 | Complete and administered by MKC Way Committee Members.
3 | 2 | 3 | 2 | Create image audit SOP | 2015-08-30 | 3.5 | 1 | 3.5 | Complete.
3 | 2 | 3 | 3 | Assign committee members to locations | 2015-09-01 | 3 | 1 | 3 | Complete.
3 | 2 | 4 | 1 | Create a checklist to track submission thru follow up | 2016-01-30 | 2.5 | 0 | 0
3 | 2 | 4 | 2 | Create a sub committee for approvals and follow through | 2016-02-28 | 2.5 | 0 | 0
3 | 2 | 4 | 3 | Come up with standards for incentives to submit and rewards for implementation | 2016-03-30 | 2.5 | 0 | 0
3 | 2 | 4 | 4 | Recognize winners at monthly manager meetings & write a newsletter article | 2015-11-30 | 2.5 | 1 | 2.5
3 | 3 | 1 | 1 | Collect the data | 2015-08-01 | 5 | 1 | 5
3 | 3 | 1 | 2 | Compile the report | 2015-09-01 | 5 | 1 | 5
3 | 3 | 2 | 1 | Define criteria and standards | 2015-08-01 | 2.5 | 1 | 2.5
3 | 3 | 2 | 2 | Finalize the 2016 budget | 2016-10-31 | 2.5 | 1 | 2.5
3 | 3 | 2 | 3 | Create baselines for each location | 2016-01-15 | 2.5 | 0 | 0
3 | 3 | 2 | 4 | Apply to LMs incentive program | 2016-02-28 | 2.5 | 0 | 0
3 | 3 | 3 | 1 | Examine development and communication scores from 2015 survey | 2015-11-01 | 2.5 | 1 | 2.5
3 | 3 | 3 | 2 | Determine date of 2016 EES | 2015-12-30 | 2.5 | 1 | 2.5
3 | 3 | 3 | 3 | Set goals for these scores and compare YOY results | 2016-08-01 | 2.5 | 0 | 0
3 | 3 | 3 | 4 | Create the target for the strategic plan scorecard | 2016-08-15 | 2.5 | 0 | 0
3 | 3 | 4 | 1 | Advertise for drivers in local retirement communities | 2015-10-15 | 3.5 | 1 | 3.5
3 | 3 | 4 | 2 | Conduct cost analysis on temp vs. FT employees (Margin Committee) | 2015-11-01 | 3.5 | 1 | 3.5
3 | 3 | 4 | 3 | Determine cost of effectiveness on H-2A Visas? | 2015-11-30 | 3 | 1 | 3
3 | 3 | 5 | 1 | Launch a sub survey from the EES-12 | 2015-12-30 | 3.5 | 0 | 0
3 | 3 | 5 | 2 | Meet with 4 different focus groups (geographical) | 2016-01-15 | 3.5 | 0 | 0
3 | 3 | 5 | 3 | Examine results and create action plan for improvement | 2016-02-28 | 3 | 0 | 0
3 | 4 | 1 | 1 | Consult with Nick, Jonathan and John for action steps | 2015-12-30 | 3.5 | 0 | 0
3 | 4 | 1 | 2 | Set up alert for january to review course of action | 2016-01-05 | 3.5 | 0 | 0
3 | 4 | 1 | 3 | Organize a meeting to draft SOP and prep for launch | 2016-02-28 | 3 | 0 | 0
3 | 4 | 2 | 1 | Create a list of metrics | 2015-08-01 | 5 | 1 | 5
3 | 4 | 2 | 2 | Set up calendar alerts to schedule quarterly panel reviews for defined HPEs in 2016 | 2015-09-01 | 5 | 1 | 5
3 | 4 | 3 | 1 | Research 3 IDP designs and create one for MKC | 2015-10-10 | 3.5 | 1 | 3.5
3 | 4 | 3 | 2 | Ensure HPEs have multiple departmental experiences; create pathways | 2016-01-15 | 3.5 | 0 | 0
3 | 4 | 3 | 3 | Set up meeting to train LMs on how to administer, maintain and log progress on new IDP template for HPEs | 2016-02-28 | 3 | 0 | 0
3 | 4 | 4 | 1 | Prep flyers to recruit teachers and include instructions for distribution | 2016-01-20 | 5 | 0 | 0
3 | 4 | 4 | 2 | Re-advertise with retirement communities | 2016-02-01 | 5 | 0 | 0
3 | 4 | 5 | 1 | Start recruiting efforts for Cloud County 2 program | 2015-11-30 | 5 | 1 | 5
3 | 4 | 5 | 2 | Log progress and effectiveness of FLM+ Sales Training program | 2016-01-15 | 5 | 0 | 0
3 | 5 | 1 | 1 | Examine wellness requirements for new benefits package | 2016-02-01 | 3.5 | 1 | 3.5
3 | 5 | 1 | 2 | Determine new courses of action | 2016-03-01 | 3.5 | 0 | 0
3 | 5 | 1 | 3 | Announce new offerings on wellness blog | 2016-05-01 | 3 | 0 | 0
4 | 1 | 1 | 1 | Prepare proforma & feasability report for outright ownership | 2015-10-01 | 4 | 1 | 4
4 | 1 | 1 | 2 | Schedule a meeting & conduct comparative analysis | 2016-01-15 | 3 | 0 | 0
4 | 1 | 1 | 3 | Determine best course of action & define new tasks | 2016-01-30 | 3 | 0 | 0
4 | 1 | 2 | 1 | Pilot tracking devices in one of each type of vehicle | 2015-10-31 | 4 | 1 | 4
4 | 1 | 2 | 2 | Purchase devices | 2015-12-01 | 3 | 1 | 3
4 | 1 | 2 | 3 | Device installation & set up | 2016-01-15 | 3 | 0 | 0
4 | 2 | 1 | 1 | Hire a manager of application development | 2015-09-05 | 10 | 1 | 10
4 | 2 | 2 | 1 | Hire a business Intelligence specialist | 2013-09-30 | 4 | 1 | 4
4 | 2 | 2 | 2 | Determine which dashboard proposals are critical | 2015-09-15 | 3 | 1 | 3
4 | 2 | 2 | 3 | Have 6-7 critical dashboards complete | 2015-12-30 | 3 | 0 | 0
4 | 3 | 1 | 1 | Ensure scorecard template is complete | 2015-06-30 | 2.5 | 1 | 2.5
4 | 3 | 1 | 2 | Determine grain quality grades | 2015-06-30 | 2.5 | 1 | 2.5
4 | 3 | 1 | 3 | Examine location's financial dashboard results | 2016-03-30 | 2.5 | 0 | 0
4 | 3 | 1 | 4 | Pilot results into new incentive program to verify feasbility | 2016-03-30 | 2.5 | 0 | 0
4 | 4 | 1 | 1 | Examine and document 5 other feed operations that are viable | 2015-10-30 | 3.5 | 1 | 3.5
4 | 4 | 1 | 2 | Determine appropriate course of action | 2015-12-30 | 3 | 0 | 0
4 | 4 | 1 | 3 | Announce new structure and create new milestones | 2016-02-28 | 3 | 0 | 0
4 | 4 | 2 | 1 | Prepare detailed outline for the BOD | 2015-11-30 | 5 | 0 | 0
4 | 4 | 2 | 2 | Post to Board Portal for review | 2015-11-30 | 5 | 0 | 0