## Perspectives
PID | Description | Progress
1 | Financial & Growth | 96.875
2 | Customer | 100
3 | Employee | 95.4
4 | Organizational Renewal | 99.375

## Initiatives
PID | INID | Description | Progress
1 | 1 | Identify key market growth areas | 100
1 | 2 | Expense management | 87.5
1 | 3 | Board Initiatve - Explore criteria for voting membership | 100
1 | 4 | Telling the MKC story to merger candidates' board members and employees | 100
2 | 1 | Maximize sales performance | 100
2 | 2 | Enhance customer experience | 100
2 | 3 | Develop strategies to target gaining business with farmers under 40 years old | 100
2 | 4 | Enhance precision ag strategy | 100
3 | 1 | Communicate the strategic plan to employee group & incorporate into their performance plan | 100
3 | 2 | Living the Four Keys: Safety, Courtesy, Image and Innovation | 100
3 | 3 | Employee engagement | 93
3 | 4 | Employee development | 84
3 | 5 | Drive employee wellness | 100
4 | 1 | Evaluate logistics effectiveness/efficiency | 100
4 | 2 | Continue to identify software platform enhancements | 100
4 | 3 | Establish education and control measures for grain handling employees | 100
4 | 4 | Analyze feed operations to optimize performance | 97.5

## Actions
PID | INID | ACTID | Description | Champion | Team | Due Date | Progress
1 | 1 | 1 | Continue discussion with potential cooperative merger partners | Darin | Dave & Senior Leadership Team | ongoing | 100
1 | 1 | 2 | Evaluate existing property upgrades to drive market growth | Jon | Darin, Erik, Steve, Dave S. | ongoing | 100
1 | 1 | 3 | Identify locations for potential greenfield sites | Dave | Ted | ongoing | 100
1 | 1 | 4 | Investigate M&A or partnerships with independent retailers | Dave | Darin, Erik, Steve, Dave S. | ongoing | 100
1 | 2 | 1 | Training on Expense Management Initiatives for key employees | Vice Presidents of Operations | Vice Presidents of Operations | 2016-02-01 | 100
1 | 2 | 2 | Investigate the value of total margin/expense management | Chris | John | 2017-02-01 | 75
1 | 3 | 1 | Investigate other methods | Dave |  | 2016-02-01 | 100
1 | 3 | 2 | Review bylaws for feasibility | Dave |  | 2016-02-01 | 100
1 | 4 | 1 | Provide talking points and other materials to be used in education and relationship-building meetings | Nichole | Executive Team, Communications | 2015-12-01 | 100
1 | 4 | 2 | Provide Board Members development opportunities to educate candidates' Board Members | Dave | Nichole | 2016-02-01 | 100
1 | 4 | 3 | Develop a Board Committee that is responsible for meetings, presentations and education of merger candidates' board members | Dave | Board of Directors | 2016-02-01 | 100
2 | 1 | 1 | Refine forecasting process to measure variances and tie to incentive | Kent | Dave S., Willie | 2016-09-01 | 100
2 | 1 | 2 | Hire Master Agronomy Advisor | Dave S. |  | ongoing | 100
2 | 1 | 3 | Develop a marketing campaign for CFA with a goal of 75 new loans | Dave S. | Nichole, Kent, Tim B. | 2016-02-01 | 100
2 | 1 | 4 | Incorporate CRM functionality to highlight priority accounts | Kent | Devin, Matt | 2015-12-01 | 100
2 | 1 | 5 | Identify and launch strategy to capture 15 new, $1 million, combined business unit accounts | Dave S. | Willie, Kent, Devin | 2016-09-01 | 100
2 | 2 | 1 | Meeting with Land O'Lakes to define MKC needs for customer portal | Matt | Dave S., Devin, Nichole, Willie, Kent | 2015-09-01 | 100
2 | 2 | 2 | Phase I Completion - Main current MKC website replacement | Matt | Dave S., Devin, Nichole, Willie, Kent | 2016-03-01 | 100
2 | 2 | 3 | Investigate online membership application, credit app, new customer packet, etc. | Matt |  | 2015-11-01 | 100
2 | 2 | 4 | Implement annual customer experience face-to-face reviews with targeted accounts | Willie | Kent, Devin, Dave S. | 2016-12-01 | 100
2 | 2 | 5 | Identify methodology to measure customer experience | Nichole | Devin, Willie, Kent, MKC Wat | 2015-12-01 | 100
2 | 2 | 6 | Establish youTube video and hold training sessions for basic navigation of existing customer portal | Nichole | Brett, Steve, Erik, Darin | 2015-11-01 | 100
2 | 2 | 7 | Continue SOP development, maintenance and management of the process | Nichole | SOP Committee | 2016-01-01 | 100
2 | 2 | 8 | Roll out changes to customer pre-pay input contracts | Danny | Willie, Kent, Dave S., Dave S. | 2015-10-15 | 100
2 | 3 | 1 | Sales training to include multi-generational selling | Willie | Devin, Kent | ongoing | 100
2 | 3 | 2 | Invite 4 growers from targeted geography to Emergin Producers Program with follow-up discussions afterward | Willie | Nichole, Devin, Kent | ongoing | 100
2 | 3 | 3 | Build Benchmarks from focus group and create S.O.P.s | Willie | Dave S., Kent, Devin, Erik | 2015-12-01 | 100
2 | 3 | 4 | Develop metrics to measure success of Emerging Producers Program through CRM | Kent | Nichole, Willie, Devin | 2016-05-01 | 100
2 | 4 | 1 | Improve website content | Ross | Craig, Dave S., Nichole | 2016-03-01 | 100
2 | 4 | 2 | Investigate potential services from UAV licensing | Ross | Craig, Dave S., GPPA | 2016-09-01 | 100
2 | 4 | 3 | Conduct 6-8 precision ag educational meetings with customers | Ross | Craig | 2016-03-01 | 100
3 | 1 | 1 | Vice Presidents and Division Managers to overview outcomes of strategic planning twice per year | Amy | VPs, DMs | ongoing | 100
3 | 1 | 2 | Create a company-wide monthly agenda for what will be communicated | Amy | Executive Team, Communications | ongoing | 100
3 | 1 | 3 | Utilize other communication methods to carry message (employee newsletter, employee portal, meeting notes, monthly employee meetings) | Amy | Kerry, Matt, Location Managers | ongoing | 100
3 | 2 | 1 | Task Safety Committee to develop methods to lower Workman's Comp rate to 0.80% or less | Jeff | Safety Committee | annually | 100
3 | 2 | 2 | Design motivational tactics to encourage courtesy |  | MKC Way Committee | 2016-02-01 | 100
3 | 2 | 3 | Continue the image audits |  | MKC Way Committee | 2016-02-01 | 100
3 | 2 | 4 | Celebrate innovation solutions awards |  | MKC Way Committee | 2016-02-01 | 100
3 | 3 | 1 | Conduct an overtime/wages study | Brett | Jeff | 2015-09-01 | 100
3 | 3 | 2 | Set standards per location to be rolled into the new incentive program | Danny | Erik, Steve, Darin, Dave S. | 2016-02-01 | 100
3 | 3 | 3 | Develop hard targets for development and communication using the engagement survey results | Brett | Jeff | 2016-02-01 | 100
3 | 3 | 4 | Investigate opportunites to improve peak-time workforce needs | Brett | Jeff | 2016-02-01 | 85
3 | 3 | 5 | Investigate opportunities to measure employee quality of life | Brett | Jeff | 2016-02-01 | 80
3 | 4 | 1 | Develop Applicator Training | Brett |  | 2016-02-01 | 75
3 | 4 | 2 | Utilize metrics to define HPE's and conduct panel review with executive team | Brett | Sr Mgmt | 2015-09-01 | 75
3 | 4 | 3 | Design PDPs for high potential employees | Brett | Jeff, Sr Mgmt | 2016-02-01 | 85
3 | 4 | 4 | Increase bench-strength and develop pool of seasonal part-time help | Jeff | Brett, Steve, Erik, Darin | 2016-02-01 | 90
3 | 4 | 5 | Create a management development program | Brett |  | 2016-02-01 | 95
3 | 5 | 1 | Investigate potential wellness providers | Hillary | Wellness Committee | 2016-05-01 | 100
4 | 1 | 1 | Continue to investigate fleet ownership feasibility versus the lease/hire option | Erik | Steve, Dave Sell, Doug, John W., Ted | ongoing | 100
4 | 1 | 2 | Compile optimal usage and functionality of Razor Tracking | Erik | Matt, Steve, Dave Sell, Doug, John W., Ted | tied to 411 | 100
4 | 2 | 1 | Hire a Manager of Applications Development | Matt | Matt | 2015-09-15 | 100
4 | 2 | 2 | Identify and complete remaining Business Intelligence and Dashboards | Matt | Danny, Tricia | ongoing | 100
4 | 3 | 1 | Incorporate managers'/superintendents' scorecard into incentive program | Brett | Steve, Erik, Jeff, Darin | 2016-02-01 | 100
4 | 4 | 1 | Explore various Feed operations structures | Dave | Erik, Darin, Steve | 2016-02-01 | 95
4 | 4 | 2 | Develop a plan to present to the Board of Directors | Dave | Erik, Darin, Steve | 2016-02-01 | 100

## Tasks
PID | INID | ACTID | TASKID | Description | Due Date | Weight | Complete | Measure
1 | 1 | 1 | 1 | Create spreadsheet with all active & prospective discussions | 2015-10-05 | 5 | 1 | 5
1 | 1 | 1 | 2 | Email spreadsheet to Darin 2 times a month to update and file | ongoing | 5 | 1 | 5
1 | 1 | 2 | 1 | Update large project list | 2015-11-11 | 5 | 1 | 5
1 | 1 | 2 | 2 | Revisit after staff meetings every other month | ongoing | 5 | 1 | 5
1 | 1 | 3 | 1 | Identify 5-6 targets | 2015-08-25 | 5 | 1 | 5
1 | 1 | 3 | 2 | Send email alert to check progress on each every 6 months | ongoing | 5 | 1 | 5
1 | 1 | 4 | 1 | Add prospective independent retailers to merger discussion spreadsheet | 2015-10-08 | 5 | 1 | 5
1 | 1 | 4 | 2 | Email spreadsheet to Darin 2 times a month to update and file | ongoing | 5 | 1 | 5
1 | 2 | 1 | 1 | Create location specific financial reports (or use current ones) | 2015-12-14 | 3.5 | 1 | 3.5
1 | 2 | 1 | 2 | Set meeting to discuss critical expense items to include on training checklist | 2015-01-20 | 3.5 | 1 | 3.5
1 | 2 | 1 | 3 | Finalize training checklist and present in monthly manager meeting | 2016-02-24 | 3 | 1 | 3
1 | 2 | 2 | 1 | Create Committee | 2015-06-11 | 2.5 | 1 | 2.5
1 | 2 | 2 | 2 | Prepare list of savings projects and prioritize by most $ saved | 2015-11-01 | 2.5 | 1 | 2.5
1 | 2 | 2 | 3 | Find ways to measure success of each project | 2015-12-31 | 2.5 | 1 | 2.5
1 | 2 | 2 | 4 | Define projects for FY 2016 and timeline them | 2016-03-01 | 2.5 | 1 | 2.5
1 | 3 | 1 | 1 | Set reminder email for Dave end of Q4 2015 | 2015-10-23 | 3.5 | 1 | 3.5
1 | 3 | 1 | 2 | Identify 2 other methods to compare to and draw up SWOTs | 2016-01-08 | 3.5 | 1 | 3.5
1 | 3 | 1 | 3 | Present results of feasability in BOD meeting | 2016-02-18 | 3 | 1 | 3
1 | 3 | 2 | 1 | Arrange meeting with Danny to review bylaws | 2016-02-05 | 3.5 | 1 | 3.5
1 | 3 | 2 | 2 | Arrange meeting with Governance Committee to review bylaws | 2016-01-30 | 3.5 | 1 | 3.5
1 | 3 | 2 | 3 | Prepare report for BOD meeting | 2016-02-11 | 3 | 1 | 3
1 | 4 | 1 | 1 | Locate talking points developed for Puerto Rico meeting | 2015-10-30 | 3.5 | 1 | 3.5
1 | 4 | 1 | 2 | Create talking points for employees to use moving forward | 2015-11-01 | 3.5 | 1 | 3.5
1 | 4 | 1 | 3 | Present in monthly manager meeting to review in team meetings | 2015-12-01 | 3 | 1 | 3
1 | 4 | 2 | 1 | Explore board of directors development programs | 2015-10-01 | 3.5 | 1 | 3.5
1 | 4 | 2 | 2 | Confirm date and time for training session | 2015-10-15 | 3.5 | 1 | 3.5
1 | 4 | 2 | 3 | Survey BOD for feedback on the session | 2016-01-14 | 3 | 1 | 3
1 | 4 | 3 | 1 | Discuss forming a committee with BOD | 2015-09-01 | 3.5 | 1 | 3.5
1 | 4 | 3 | 2 | Consider adding the responsibility to an existing BOD committee or develop all members | 2015-10-01 | 3.5 | 1 | 3.5
1 | 4 | 3 | 3 | Make a decision | 2016-02-01 | 3 | 1 | 3
2 | 1 | 1 | 1 | Discuss the methodology to forecast properly | 2016-02-01 | 3 | 1 | 3
2 | 1 | 1 | 2 | Build a better forecasting tool | 2016-04-01 | 3.5 | 1 | 3.5
2 | 1 | 1 | 3 | Tie it to incentive plan | 2016-09-01 | 3.5 | 1 | 3.5
2 | 1 | 2 | 1 | Hire Master Agronomy Advisor | 2015-11-30 | 10 | 1 | 10
2 | 1 | 3 | 1 | Push out CFA Postcards | 2015-10-30 | 2.5 | 1 | 2.5
2 | 1 | 3 | 2 | Create a target list and present to Dave Spears | 2015-11-30 | 2.5 | 1 | 2.5
2 | 1 | 3 | 3 | Complete all 1 on 1 visits with Field Marketers | 2015-12-31 | 2.5 | 1 | 2.5
2 | 1 | 3 | 4 | Progress report on all new CFA loans to Dave Spears | 2016-01-30 | 2.5 | 1 | 2.5
2 | 1 | 4 | 1 | Sign integration agreement with PowerObjects | 2015-11-01 | 2.5 | 1 | 2.5
2 | 1 | 4 | 2 | Define acceptable length of days with no contact | 2015-11-15 | 2.5 | 1 | 2.5
2 | 1 | 4 | 3 | Create alerts to push out every Monday to Field Marketers | 2015-12-10 | 2.5 | 1 | 2.5
2 | 1 | 4 | 4 | Create report to send out to Managers once a month | 2015-12-30 | 2.5 | 1 | 2.5
2 | 1 | 5 | 1 | Willie and Kent provide Dave Spears a list of targeted growth accounts | 2015-12-01 | 3.5 | 1 | 3.5
2 | 1 | 5 | 2 | Willie and Kent checkpoint with Dave Spears | 2015-04-30 | 3 | 1 | 3
2 | 1 | 5 | 3 | Willie and Kent continue go to market strategy | 2015-08-31 | 3.5 | 1 | 3.5
2 | 2 | 1 | 1 | Invite LOL to Groveland for a meeting | 2015-08-28 | 5 | 1 | 5
2 | 2 | 1 | 2 | Follow up with LOL and receive milestone timeline | 2015-09-30 | 5 | 1 | 5
2 | 2 | 2 | 1 | Task 1 | ongoing | 2.5 | 1 | 2.5
2 | 2 | 2 | 2 | Task 2 | ongoing | 3.5 | 1 | 3.5
2 | 2 | 2 | 3 | Task 3 | ongoing | 4 | 1 | 4
2 | 2 | 3 | 1 | Investigation | ongoing | 10 | 1 | 10
2 | 2 | 4 | 1 | Choose method to administer review; possibly CRM | 2015-11-01 | 2.5 | 1 | 2.5
2 | 2 | 4 | 2 | Come up with 7 universal questions | 2015-12-15 | 2.5 | 1 | 2.5
2 | 2 | 4 | 3 | Define accounts and schedule reviews | 2016-01-30 | 2.5 | 1 | 2.5
2 | 2 | 4 | 4 | Collect data and create action plans for Field Marketers | 2016-03-30 | 2.5 | 1 | 2.5
2 | 2 | 5 | 1 | Investigate CRM capabilities | 2015-11-01 | 3.5 | 1 | 3.5
2 | 2 | 5 | 2 | Define measrues of engagement | 2015-11-15 | 3 | 1 | 3
2 | 2 | 5 | 3 | Have a survey meeting to define types and targets | 2015-11-20 | 3.5 | 1 | 3.5
2 | 2 | 6 | 1 | Meet with IT to understand portal modules | 2015-10-10 | 2.5 | 1 | 2.5
2 | 2 | 6 | 2 | Map and script the content | 2015-10-30 | 2.5 | 1 | 2.5
2 | 2 | 6 | 3 | Troubleshoot the flow | 2015-11-30 | 2.5 | 1 | 2.5
2 | 2 | 6 | 4 | Record final version and set up training schedule | 2015-12-30 | 2.5 | 1 | 2.5
2 | 2 | 7 | 1 | Create SOP Committee and choose SOP template | 2015-01-30 | 3.5 | 1 | 3.5
2 | 2 | 7 | 2 | Begin process transfers into new template | 2015-02-01 | 3.5 | 1 | 3.5
2 | 2 | 7 | 3 | Continue to transfer processes; last count 106 | 2015-11-30 | 3 | 1 | 3
2 | 2 | 8 | 1 | Decide upon 4 new types of pre-pay contracts | 2015-08-10 | 1 | 1 | 1
2 | 2 | 8 | 2 | Go through due diligence for each one | 2015-09-30 | 2 | 1 | 2
2 | 2 | 8 | 3 | Have seed & fertilizer contracts complete | 2015-10-15 | 1 | 1 | 1
2 | 2 | 8 | 4 | Have energy and CP contracts complete | 2015-12-15 | 2 | 1 | 2
2 | 2 | 8 | 5 | Lawyer assessments and approvals for all contracts | 2015-12-30 | 2 | 1 | 2
2 | 2 | 8 | 6 | Formal training for key employees on all contracts | 2016-01-30 | 2 | 1 | 2
2 | 3 | 1 | 1 | Determine source and curriculum for training | 2015-09-01 | 2.5 | 1 | 2.5
2 | 3 | 1 | 2 | Acquire training schedule through FLM+ | 2015-10-01 | 2.5 | 1 | 2.5
2 | 3 | 1 | 3 | Discuss effectiveness of administration of topic | 2015-12-30 | 2.5 | 1 | 2.5
2 | 3 | 1 | 4 | Consider guest speakers to enhance effectiveness | 2016-01-15 | 2.5 | 1 | 2.5
2 | 3 | 2 | 1 | Compile list of invitees to include Sumner County | 2015-11-15 | 2.5 | 1 | 2.5
2 | 3 | 2 | 2 | Send out invitations | 2015-11-30 | 2.5 | 1 | 2.5
2 | 3 | 2 | 3 | Ensure Field Marketers made invitational follow up calls | 2015-12-01 | 2.5 | 1 | 2.5
2 | 3 | 2 | 4 | Set up internal meeting to discuss info collected from follow up | 2016-01-29 | 2.5 | 1 | 2.5
2 | 3 | 3 | 1 | Consider FBN software | 2015-11-01 | 3 | 1 | 3
2 | 3 | 3 | 2 | Run a pilot on a few producers and collect data | 2015-12-15 | 3.5 | 1 | 3.5
2 | 3 | 3 | 3 | Set up a meeting to discuss results and how to move forward | 2015-12-30 | 3.5 | 1 | 3.5
2 | 3 | 4 | 1 | Create survey questions to launch after EPP | 2016-01-10 | 2.5 | 1 | 2.5
2 | 3 | 4 | 2 | Launch through CRM | 2016-01-22 | 2.5 | 1 | 2.5
2 | 3 | 4 | 3 | Discuss results and log changes for next year | 2016-03-01 | 2.5 | 1 | 2.5
2 | 3 | 4 | 4 | Begin planning EPP 2017 | 2016-05-01 | 2.5 | 1 | 2.5
2 | 4 | 1 | 1 | Provide LOL current precision ag data for phase 1 | 2015-09-30 | 3.5 | 1 | 3.5
2 | 4 | 1 | 2 | Continue to collect new content & ideas to prepare for updates | 2016-02-15 | 3.5 | 1 | 3.5
2 | 4 | 1 | 3 | Evaluate new website and update as necessary | 2016-03-30 | 3 | 1 | 3
2 | 4 | 2 | 1 | Obtain UAV licensing | 2016-01-30 | 3 | 1 | 3
2 | 4 | 2 | 2 | Make a list of services offered or intended to offer | 2016-02-28 | 3.5 | 1 | 3.5
2 | 4 | 2 | 3 | Discuss marketing options for selected UAV services | 2016-04-01 | 3.5 | 1 | 3.5
2 | 4 | 3 | 1 | Prepare a schedule with dates, times & locations for new year | 2015-12-05 | 3 | 1 | 3
2 | 4 | 3 | 2 | Discuss marketing collateral needs and timelines | 2015-12-30 | 3.5 | 1 | 3.5
2 | 4 | 3 | 3 | Collect information from customers & discuss results in Monthly Managers meetings | 2016-03-30 | 3.5 | 1 | 3.5
3 | 1 | 1 | 1 | Schedule dates for planning sessions (Aug & Jan) | 2015-06-01 | 3.5 | 1 | 3.5
3 | 1 | 1 | 2 | Schedule date for recap @ monthly manager meeting (March) | 2015-09-01 | 3.5 | 1 | 3.5
3 | 1 | 1 | 3 | Schedule date for VIP meeting (Dec) | 2015-11-11 | 3 | 1 | 3
3 | 1 | 2 | 1 | Create a scheduke & review template for each initiative to cover 1 in every monthly manager's meeting | 2015-08-30 | 3.5 | 1 | 3.5
3 | 1 | 2 | 2 | Create universal team meeting agenda template to include above intiatives in review | 2015-09-30 | 3.5 | 1 | 3.5
3 | 1 | 2 | 3 | Create a synopsis of each initiative including interactive talking points | 2016-12-30 | 3 | 1 | 3
3 | 1 | 3 | 1 | Publish a newsletter article relative to the initiatives in review monthly | 2016-12-30 | 2.5 | 1 | 2.5
3 | 1 | 3 | 2 | Put initiatives in review on M-Drive for all user access | 2016-12-30 | 2.5 | 1 | 2.5
3 | 1 | 3 | 3 | Visit 3-4 team meetings/month to ensure consistency | 2016-12-30 | 2.5 | 1 | 2.5
3 | 1 | 3 | 4 | Ensure Champions are prepared to present intiatives in review at onthly manager's meetings | 2016-12-30 | 2.5 | 1 | 2.5
3 | 2 | 1 | 1 | Create weekly safety messages and distribute eery Monday | 2015-02-01 | 1 | 1 | 1
3 | 2 | 1 | 2 | Create SOP for prescription eye protection | 2015-04-30 | 1 | 1 | 1
3 | 2 | 1 | 3 | Implement driver training program | 2015-06-30 | 2 | 1 | 2
3 | 2 | 1 | 4 | Revise the hot work permit SOP | 2015-04-30 | 2 | 1 | 2
3 | 2 | 1 | 5 | Create consistent platform for tailgate safety talks | 2016-03-01 | 2 | 1 | 2
3 | 2 | 1 | 6 | Perform location safety audits | 2016-06-30 | 2 | 1 | 2
3 | 2 | 2 | 1 | Create monthly customer service topic for review in team meetings | 2015-12-01 | 10 | 1 | 10
3 | 2 | 3 | 1 | Redesign image audit template | 2015-08-01 | 3.5 | 1 | 3.5
3 | 2 | 3 | 2 | Create image audit SOP | 2015-08-30 | 3.5 | 1 | 3.5
3 | 2 | 3 | 3 | Assign committee members to locations | 2015-09-01 | 3 | 1 | 3
3 | 2 | 4 | 1 | Create a checklist to track submission thru follow up | 2016-01-30 | 2.5 | 1 | 2.5
3 | 2 | 4 | 2 | Create a sub committee for approvals and follow through | 2016-02-28 | 2.5 | 1 | 2.5
3 | 2 | 4 | 3 | Come up with standards for incentives to submit and rewards for implementation | 2016-03-30 | 2.5 | 1 | 2.5
3 | 2 | 4 | 4 | Recognize winners at monthly manager meetings & write a newsletter article | 2015-11-30 | 2.5 | 1 | 2.5
3 | 3 | 1 | 1 | Collect the data | 2015-08-01 | 5 | 1 | 5
3 | 3 | 1 | 2 | Compile the report | 2015-09-01 | 5 | 1 | 5
3 | 3 | 2 | 1 | Define criteria and standards | 2015-08-01 | 2.5 | 1 | 2.5
3 | 3 | 2 | 2 | Finalize the 2016 budget | 2016-10-31 | 2.5 | 1 | 2.5
3 | 3 | 2 | 3 | Create baselines for each location | 2016-01-15 | 2.5 | 1 | 2.5
3 | 3 | 2 | 4 | Apply to LMs incentive program | 2016-02-28 | 2.5 | 1 | 2.5
3 | 3 | 3 | 1 | Examine development and communication scores from 2015 survey | 2015-11-01 | 2.5 | 1 | 2.5
3 | 3 | 3 | 2 | Determine date of 2016 EES | 2015-12-30 | 2.5 | 1 | 2.5
3 | 3 | 3 | 3 | Set goals for these scores and compare YOY results | 2016-08-01 | 2.5 | 1 | 2.5
3 | 3 | 3 | 4 | Create the target for the strategic plan scorecard | 2016-08-15 | 2.5 | 1 | 2.5
3 | 3 | 4 | 1 | Advertise for drivers in local retirement communities | 2015-10-15 | 3.5 | 1 | 3.5
3 | 3 | 4 | 2 | Conduct cost analysis on temp vs. FT employees (Margin Committee) | 2015-11-01 | 3.5 | 1 | 3.5
3 | 3 | 4 | 3 | Determine cost of effectiveness on H-2A Visas? | TBD | 3 | 0 | 0
3 | 3 | 5 | 1 | Launch a sub survey from the EES-12 | 2015-12-30 | 3.5 | 1 | 3.5
3 | 3 | 5 | 2 | Meet with 4 different focus groups (geographical) | 2016-01-15 | 3.5 | 1 | 3.5
3 | 3 | 5 | 3 | Examine results and create action plan for improvement | 2016-02-28 | 3 | 1 | 3
3 | 4 | 1 | 1 | Consult with Nick, Jonathan and John for action steps | 2015-12-30 | 3.5 | 1 | 3.5
3 | 4 | 1 | 2 | Set up alert for january to review course of action | 2016-01-05 | 3.5 | 1 | 3.5
3 | 4 | 1 | 3 | Organize a meeting to draft SOP and prep for launch | 2016-02-28 | 3 | 1 | 3
3 | 4 | 2 | 1 | Create a list of metrics | 2015-08-01 | 5 | 1 | 5
3 | 4 | 2 | 2 | Set up calendar alerts to schedule quarterly panel reviews for defined HPEs in 2016 | 2015-09-01 | 5 | 1 | 5
3 | 4 | 3 | 1 | Research 3 IDP designs and create one for MKC | 2015-10-10 | 3.5 | 1 | 3.5
3 | 4 | 3 | 2 | Ensure HPEs have multiple departmental experiences; create pathways | 2016-01-15 | 3.5 | 1 | 3.5
3 | 4 | 3 | 3 | Set up meeting to train LMs on how to administer, maintain and log progress on new IDP template for HPEs | 2016-02-28 | 3 | 1 | 3
3 | 4 | 4 | 1 | Prep flyers to recruit teachers and include instructions for distribution | 2016-01-20 | 5 | 1 | 5
3 | 4 | 4 | 2 | Re-advertise with retirement communities | 2016-02-01 | 5 | 1 | 5
3 | 4 | 5 | 1 | Start recruiting efforts fro Cloud County 2 program | 2015-11-30 | 5 | 1 | 5
3 | 4 | 5 | 2 | Log progress and effectiveness of FLM+ Sales Training program | 2016-01-15 | 5 | 1 | 5
3 | 5 | 1 | 1 | Examine wellness requirements for new benefits package | 2016-02-01 | 3.5 | 1 | 3.5
3 | 5 | 1 | 2 | Determine new courses of action | 2016-03-01 | 3.5 | 1 | 3.5
3 | 5 | 1 | 3 | Announce new offerings on wellness blog | 2016-05-01 | 3 | 1 | 3
4 | 1 | 1 | 1 | Prepare proforma & feasability report for outright ownership | 2015-10-01 | 4 | 1 | 4
4 | 1 | 1 | 2 | Schedule a meeting & conduct comparative analysis | 2016-01-15 | 3 | 1 | 3
4 | 1 | 1 | 3 | Determine best course of action & define new tasks | 2016-01-30 | 3 | 1 | 3
4 | 1 | 2 | 1 | Pilot tracking devices in one of each type of vehicle | 2015-10-31 | 4 | 1 | 4
4 | 1 | 2 | 2 | Purchase devices | 2015-12-01 | 3 | 1 | 3
4 | 1 | 2 | 3 | Device installation & set up | 2016-01-15 | 3 | 1 | 3
4 | 2 | 1 | 1 | Hire a manager of application development | 2015-09-05 | 10 | 1 | 10
4 | 2 | 2 | 1 | Hire a business Intelligence Specialist | 2013-09-30 | 4 | 1 | 4
4 | 2 | 2 | 2 | Determine which dashboard proposals are critical | 2015-09-15 | 3 | 1 | 3
4 | 2 | 2 | 3 | Have 6-7 critical dashboards complete | 2015-12-30 | 3 | 1 | 3
4 | 3 | 1 | 1 | Ensure scorecard template is complete | 2015-06-30 | 2.5 | 1 | 2.5
4 | 3 | 1 | 2 | Determine grain quality grades | 2015-06-30 | 2.5 | 1 | 2.5
4 | 3 | 1 | 3 | Examine location's financial dashboard results | 2016-03-30 | 2.5 | 1 | 2.5
4 | 3 | 1 | 4 | Pilot results into new incentive program to verify feasbility | 2016-03-30 | 2.5 | 1 | 2.5
4 | 4 | 1 | 1 | Examine and document 5 other feed operations that are viable | 2015-10-30 | 3.5 | 1 | 3.5
4 | 4 | 1 | 2 | Determine appropriate course of action | 2015-12-30 | 3 | 1 | 3
4 | 4 | 1 | 3 | Announce new structure and create new milestones | 2016-02-28 | 3 | 1 | 3
4 | 4 | 2 | 1 | Prepare detailed outline for the BOD | 2015-11-30 | 5 | 1 | 5
4 | 4 | 2 | 2 | Post to Board Portal for review | 2015-11-30 | 5 | 1 | 5
Formulas:
Complete = IF([Due Date]>TODAY(),1,0)