## Perspectives
PID | Description | Progress
1 | Financial & Growth | 8.3333
2 | Customer | 38.9137
3 | Employee | 21
4 | Organizational Renewal | 6.6667

## Initiatives
PID | INID | Description | Progress | notes
1 | 1 | Identify key market growth areas | 16.6667
1 | 2 | Expense management | 0
2 | 1 | Maximize sales performance | 53.75
2 | 2 | Enhance customer experience | 18.5714
2 | 3 | Develop strategies to target gaining business with farmers under 40 years old | 33.3333
2 | 4 | Enhance precision ag strategy | 50
3 | 1 | Communicate the strategic plan to employee group & incorporate into their incentive plan | 0
3 | 2 | Living the Four Keys: Safety, Courtesy, Image and Innovation | 12.5
3 | 3 | Employee engagement | 42.5
3 | 4 | Employee development | 50
3 | 5 | Drive employee wellness | 0
4 | 1 | Evaluate logistics effectiveness/efficiency | 0
4 | 2 | Continue to identify software platform enhancements | 0
4 | 3 | Develop strategy for locations affected by the TMA structure changes | 0
4 | 4 | Develop Sumner County business plan | 40
4 | 5 | Prepare for hybrid wheat opportunity | 0
4 | 6 | Develop plans around strategic partnerships | 0
-

## Actions
PID | INID | ACTID | Description | Champion | Team | Due Date | Progress | Notes
1 | 1 | 1 | Continue discussion with potential cooperative merger partners & independent retailers | Darin | Dave & Senior Leadership Team | 2017-02-01 | 50
1 | 1 | 2 | Evaluate existing property upgrades to drive market growth | Jon | Darin, Erik, Steve, Dave S. | 2017-02-01 | 0
1 | 1 | 3 | Identify locations for potential greenfield sites | Dave | Ted | 2017-02-01 | 0
1 | 2 | 1 | Training on Expense Management Initiatives for key employees | Vice Presidents of Operations | Vice Presidents of Operations | 2016-07-01 | 0
1 | 2 | 2 | Investigate the value of total margin/expense management | Chris | John | 2017-02-01 | 0
1 | 2 | 3 | Analyze the cost of operating ground piles vs. building vertical storage | Erik | Danny | 2017-02-01 | 0
2 | 1 | 1 | Refine forecasting process to measure variances and tie to incentive | Kent | Dave S., Willie | 2016-09-01 | 30
2 | 1 | 2 | Develop a marketing campaign for CFA with a goal of 75 new loans | Dave S. | Nichole, Kent, Tim B. | 2016-02-01 | 100
2 | 1 | 3 | Incorporate CRM functionality to highlight priority accounts | Kent | Devin, Matt | 2016-04-01 | 50
2 | 1 | 4 | Identify and launch strategy to capture 15 new, $1 million, combined business unit accounts | Dave S. | Willie, Kent, Devin | 2016-09-01 | 35
2 | 2 | 1 | Investigate online membership application, credit app, new customer packet, etc. | Matt |  | 2016-12-01 | 0
2 | 2 | 2 | Implement annual customer experience face-to-face reviews with targeted accounts | Willie | Kent, Devin, Dave S. | 2016-12-01 | 80
2 | 2 | 3 | Identify methodology to measure customer experience | Nichole | Devin, Willie, Kent, MKC Way | 2017-02-01 | 0
2 | 2 | 4 | Establish YouTube video and hold training sessions for basic navigation of existing customer portal | Nichole | Brett, Steve, Erik, Darin | 2016-04-01 | 50
2 | 2 | 5 | Roll out changes to customer pre-pay input contracts | Danny | Willie, Kent, Dave S., Dave S. | 2016-06-01 | 0
2 | 2 | 6 | Explore opportunities for a cattle risk management offer | Devin |  | 2016-05-01 | 0
2 | 2 | 7 | Phase 2 (website replacement) Enhance grower portal | Matt |  | 2017-02-01 | 0
2 | 3 | 1 | Create development plans based on generational sales training | Willie | Devin, Kent | 2017-02-01 | 0
2 | 3 | 2 | Build Benchmarks from focus group and create S.O.P.s | Willie | Dave S., Kent, Devin, Erik | 2016-08-01 | 0
2 | 3 | 3 | Develop metrics to measure success of Emerging Producers Program through CRM | Kent | Nichole, Willie, Devin | 2016-05-01 | 100
2 | 4 | 1 | Improve website content | Ross | Craig, Dave S., Nichole | 2016-03-01 | 70
2 | 4 | 2 | Investigate potential services from UAV licensing | Ross | Craig, Dave S., GPPA | 2016-09-01 | 65
2 | 4 | 3 | Conduct 6-8 precision ag educational meetings with customers | Ross | Craig | 2016-03-01 | 65
2 | 4 | 4 | Investigate new precision ag software platform | Mandie | Ross, Matt, Craig, Troy, Dave, Kent | 2016-05-01 | 0
3 | 1 | 1 | Vice Presidents and Division Managers to overview outcomes of strategic planning twice per year via performance plans | Amy | VPs, DMs | 2017-02-01 | 0
3 | 1 | 2 | Utilize other communication methods to carry message | Amy | Nichole, Matt, Location Managers | 2017-02-01 | 0
3 | 2 | 1 | Safety-I practice safe behaviors in everything I do | MKC Way Committee | Jeff, Safety Committee | 2017-02-01 | 0
3 | 2 | 2 | Courtesy-I always service the customer with convenience and ease | MKC Way Committee | MKC Way Committee | 2017-02-01 | 50
3 | 2 | 3 | Image-I practice being a good steward to the community | MKC Way Committee | MKC Way Committee | 2017-02-01 | 0
3 | 2 | 4 | Innovation-I am willing to learn and be knowledgeable | MKC Way Committee | MKC Way Committee | 2017-02-01 | 0
3 | 3 | 1 | Set standards per location to be rolled into the new incentive program | Danny | Erik, Steve, Darin, Dave S. | 2016-04-01 | 50
3 | 3 | 2 | Develop hard targets for development and communication using the engagement survey results | Brett | Jeff | 2016-04-01 | 50
3 | 3 | 3 | Investigate opportunities to improve peak-time workforce needs | Brett | Jeff | 2016-08-01 | 35
3 | 3 | 4 | Investigate opportunities to measure employee quality of life | Brett | Jeff | 2016-08-01 | 35
3 | 4 | 1 | Utilize metrics to define HPE's and conduct panel review with executive team | Brett | Sr Mgmt | 2016-08-01 | 50
3 | 4 | 2 | Design IDPs for high potential employees | Brett | Jeff, Sr Mgmt | 2016-04-01 | 50
3 | 4 | 3 | Increase bench-strength and develop pool of seasonal part-time help | Jeff | Brett, Steve, Erik, Darin | 2016-08-01 | 50
3 | 5 | 1 | Develop biometric screening program for MKC employees and families | Hillary | Wellness Committee | 2016-11-01 | 0
3 | 5 | 2 | Develop an activity program for employees and their families | Hillary | Wellness Committee | 2016-03-01 | 0
3 | 5 | 3 | Develop wellness education opportunities for employees and their families | Hillary | Wellness Committee | 2016-03-01 | 0
3 | 5 | 4 | Investigate and implement reward opportunities for employees and their families for participation in wellness activities | Hillary | Wellness Committee | 2016-04-01 | 0
4 | 1 | 1 | Prepare action plans for fleet ownership and lease/hire option | Erik | Steve, Dave Sell, Doug, John W., Ted | 2016-08-01 | 0
4 | 1 | 2 | Compile optimal usage and functionality of Razor Tracking | Erik | Matt, Steve, Dave Sell, Doug, John W., Ted | 2017-02-01 | 0
4 | 2 | 1 | Complete phase 1 & phase 2 of Business Intelligence Dashboard development | Matt | Mandie, Aric | 2016-06-01 | 0
4 | 2 | 2 | Communicate and implement company wide software project approach | Matt | Mandie, Aric | 2016-05-01 | 0
4 | 2 | 3 | Develop an annual plan to review processes and procedures in our ERP system | Matt | Systems Ops Team | 2016-12-01 | 0
4 | 2 | 4 | Evaluate current grain software platform | Matt | Tricia, Danny | 2017-01-01 | 0
4 | 3 | 1 | Identify locations | Danny | VPs, Ted | 2016-06-01 | 0
4 | 3 | 2 | Create action plans for each location | Danny | VPs, Ted | 2017-02-01 | 0
4 | 4 | 1 | Navigate governmental requirements | Erik |  | 2016-06-01 | 0
4 | 4 | 2 | Complete facility design | Jon |  | 2016-03-01 | 100
4 | 4 | 3 | Prepare communications plan | Nichole | Erik | 2016-08-01 | 100
4 | 4 | 4 | Establish grain, agronomy, risk mgmt., energy plan | Erik | Dave Sell, Dave Spears, Devin | 2016-08-01 | 0
4 | 4 | 5 | Establish HR model | Brett | Jeff, Erik | 2016-08-01 | 0
4 | 5 | 1 |  |  |  |  | 0
4 | 5 | 2 |  |  |  |  | 0
4 | 6 | 1 | Prepare feed mill plans | Dave C. |  | 2016-06-01 | 0
4 | 6 | 2 | Prepare for agronomy in Canton | Dave Spears | Erik, Kent | 2016-06-01 | 0

## Tasks
PID | INID | ACTID | TASKID | Description | Due Date | Weight | Complete | Measure
1 | 1 | 1 | 1 | Email spreadsheet to Darin 2 times a month to update and file | 2016-03-01 | 5 | 1 | 5
1 | 1 | 1 | 2 | Set up 2 visits a month | 2016-03-01 | 5 | 0 | 0
1 | 1 | 2 | 1 | Update large project list in JUL | 2016-07-01 | 5 | 0 | 0
1 | 1 | 2 | 2 | Update large project list in DEC | 2016-12-01 | 5 | 0 | 0
1 | 1 | 3 | 1 | Send email alert to check progress in JUL | 2016-07-01 | 5 | 0 | 0
1 | 1 | 3 | 2 | Send email alert to check progress in DEC | 2016-12-01 | 5 | 0 | 0
1 | 2 | 1 | 1 | Create location specific financial reports | 2016-06-01 | 3.5 | 0 | 0
1 | 2 | 1 | 2 | Set meeting to discuss critical expense items to include on training checklist | 2016-06-01 | 3.5 | 0 | 0
1 | 2 | 1 | 3 | Finalize training checklist and present in monthly manager meeting | 2016-07-01 | 3 | 0 | 0
1 | 2 | 2 | 1 | Identify priority projects for the year | 2016-04-01 | 2.5 | 0 | 0
1 | 2 | 2 | 2 | Choose dates to join Staff Meetings for periodic review | 2016-06-01 | 2.5 | 0 | 0
1 | 2 | 2 | 3 | Find ways to measure success of each project | 2016-08-01 | 2.5 | 0 | 0
1 | 2 | 2 | 4 | Define projects for FY 2018 and timeline them | 2017-02-01 | 2.5 | 0 | 0
1 | 2 | 3 | 1 | Build proforma for both ground piles and vertical storage-include different sizes and construction materials | 2016-07-01 | 5 | 0 | 0
1 | 2 | 3 | 2 | Schedule a meeting with Danny to prepare notes for August retreat | 2016-08-01 | 5 | 0 | 0
2 | 1 | 1 | 1 | Discuss the methodology to forecast properly | 2016-02-01 | 3 | 1 | 3
2 | 1 | 1 | 2 | Build a better forecasting tool | 2016-04-01 | 3.5 | 0 | 0
2 | 1 | 1 | 3 | Tie it to incentive plan | 2016-09-01 | 3.5 | 0 | 0
2 | 1 | 2 | 1 | Push out CFA Postcards | 2015-10-30 | 2.5 | 1 | 2.5
2 | 1 | 2 | 2 | Create a target list and present to Dave Spears | 2015-11-30 | 2.5 | 1 | 2.5
2 | 1 | 2 | 3 | Complete all 1 on 1 visits with Field Marketers | 2015-12-31 | 2.5 | 1 | 2.5
2 | 1 | 2 | 4 | Progress report on all new CFA loans to Dave Spears | 2016-01-30 | 2.5 | 1 | 2.5
2 | 1 | 3 | 1 | Sign integration agreement with PowerObjects | 2015-11-01 | 2.5 | 1 | 2.5
2 | 1 | 3 | 2 | Define acceptable length of days with no contact | 2015-11-15 | 2.5 | 1 | 2.5
2 | 1 | 3 | 3 | Create dashboard to push out every Monday to Field Marketers | 2016-03-01 | 2.5 | 0 | 0
2 | 1 | 3 | 4 | Create report to send out to Managers weekly | 2016-04-01 | 2.5 | 0 | 0
2 | 1 | 4 | 1 | Willie and Kent provide Dave Spears a list of targeted growth accounts | 2015-12-01 | 3.5 | 1 | 3.5
2 | 1 | 4 | 2 | Willie and Kent checkpoint with Dave Spears | 2016-04-30 | 3 | 0 | 0
2 | 1 | 4 | 3 | Willie and Kent continue go to market strategy | 2016-08-31 | 3.5 | 0 | 0
2 | 2 | 1 | 1 | Get with Matt about online membership application tasks and timelines |  | 5 | 0 | 0
2 | 2 | 1 | 2 |  |  | 5 | 0 | 0
2 | 2 | 2 | 1 | Investigation | 2016-09-15 | 2 | 1 | 2
2 | 2 | 2 | 2 | Choose method to administer review; possibly CRM | 2015-11-01 | 2 | 1 | 2
2 | 2 | 2 | 3 | Come up with 7 universal questions | 2015-12-15 | 2 | 1 | 2
2 | 2 | 2 | 4 | Define accounts and schedule reviews | 2016-01-30 | 2 | 1 | 2
2 | 2 | 2 | 5 | Collect data and create action plans for Field Marketers | 2016-03-30 | 2 | 0 | 0
2 | 2 | 3 | 1 | Finalize fixed survey calendar and all survey questions | 2016-04-01 | 3.5 | 0 | 0
2 | 2 | 3 | 2 | Determine how to generate end of work flow random selection surveys | 2016-06-01 | 3 | 0 | 0
2 | 2 | 3 | 3 | Schedule meetings to evaluate findings based on engagement metrics (share of wallet-60, meetings-20, surveys-20) | 2017-02-01 | 3.5 | 0 | 0
2 | 2 | 4 | 1 | Meet with IT to understand portal modules | 2015-10-10 | 2.5 | 1 | 2.5
2 | 2 | 4 | 2 | Map and script the content | 2015-10-30 | 2.5 | 1 | 2.5
2 | 2 | 4 | 3 | Troubleshoot the flow | 2016-03-15 | 2.5 | 0 | 0
2 | 2 | 4 | 4 | Record final version and set up training schedule | 2016-04-01 | 2.5 | 0 | 0
2 | 2 | 5 | 1 | Finalize energy contracts | 2016-04-01 | 3.5 | 0 | 0
2 | 2 | 5 | 2 | Schedule formal training for new contracts | 2016-05-01 | 3.5 | 0 | 0
2 | 2 | 5 | 3 | Evaluate effectiveness of all new contracts | 2016-06-01 | 3 | 0 | 0
2 | 2 | 6 | 1 | Make a list of all current and new offerings to producers | 2016-03-15 | 2 | 0 | 0
2 | 2 | 6 | 2 | Send out a survey of qualifing questions to targeted group of producers | 2016-03-30 | 2 | 0 | 0
2 | 2 | 6 | 3 | Set up 3 LRP/PRF meetings (choose locations) | 2016-04-15 | 2 | 0 | 0
2 | 2 | 6 | 4 | Formalize offerings | 2016-06-15 | 2 | 0 | 0
2 | 2 | 6 | 5 | Clarify marketing and sales processes for new livestock risk management offerings | 2016-08-01 | 2 | 0 | 0
2 | 2 | 7 | 1 | Get with Matt about Phase 2-enhance grower portal tasks and timelines |  | 2.5 | 0 | 0
2 | 2 | 7 | 2 |  |  | 2.5 | 0 | 0
2 | 2 | 7 | 3 |  |  | 2.5 | 0 | 0
2 | 2 | 7 | 4 |  |  | 2.5 | 0 | 0
2 | 3 | 1 | 1 | Create development plan template | 2016-04-01 | 2.5 | 0 | 0
2 | 3 | 1 | 2 | Schedule review sessions | 2016-05-01 | 2.5 | 0 | 0
2 | 3 | 1 | 3 | Create a ride along calendar | 2016-06-01 | 2.5 | 0 | 0
2 | 3 | 1 | 4 | Discuss effectiveness of CRM internal communication tool | 2016-12-01 | 2.5 | 0 | 0
2 | 3 | 2 | 1 | Decide what precision ag program will look like | 2016-04-01 | 3 | 0 | 0
2 | 3 | 2 | 2 | Send requirements to multiple companies for the software piece & choose one with benchmarking capability | 2016-06-01 | 3.5 | 0 | 0
2 | 3 | 2 | 3 | Pilot benchmarking functionality | 2016-08-01 | 3.5 | 0 | 0
2 | 3 | 3 | 1 | Create survey questions to launch after EPP | 2016-01-10 | 2.5 | 1 | 2.5
2 | 3 | 3 | 2 | Launch through CRM | 2016-01-22 | 2.5 | 1 | 2.5
2 | 3 | 3 | 3 | Discuss results and log changes for next year | 2016-03-01 | 2.5 | 1 | 2.5
2 | 3 | 3 | 4 | Begin planning EPP 2017 | 2016-05-01 | 2.5 | 1 | 2.5
2 | 4 | 1 | 1 | Provide LOL current precision ag data for Phase 1 | 2015-09-30 | 3.5 | 1 | 3.5
2 | 4 | 1 | 2 | Continue to collect new content & ideas to prepare for updates | 2016-02-15 | 3.5 | 1 | 3.5
2 | 4 | 1 | 3 | Evaluate new website and update as necessary | 2016-03-30 | 3 | 0 | 0
2 | 4 | 2 | 1 | Submit for UAV licensing | 2016-01-30 | 3 | 1 | 3
2 | 4 | 2 | 2 | Make a list of services offered or intended to offer | 2016-02-28 | 3.5 | 1 | 3.5
2 | 4 | 2 | 3 | Discuss marketing options for selected UAV services | 2016-04-01 | 3.5 | 0 | 0
2 | 4 | 3 | 1 | Prepare a schedule with dates, times & locations for new year | 2015-12-05 | 3 | 1 | 3
2 | 4 | 3 | 2 | Discuss marketing collateral needs and timelines | 2015-12-30 | 3.5 | 1 | 3.5
2 | 4 | 3 | 3 | Collect information from customers & discuss results in Monthly Managers meetings | 2016-03-30 | 3.5 | 0 | 0
2 | 4 | 4 | 1 | Brainstorming sessions for gathering requirements | 2016-03-15 | 2 | 0 | 0
2 | 4 | 4 | 2 | Compile requirements list | 2016-03-31 | 2 | 0 | 0
2 | 4 | 4 | 3 | Send out RFP to several vendors with our requirements | 2016-04-05 | 2 | 0 | 0
2 | 4 | 4 | 4 | Evaluate proposal submitted by vendors | 2016-04-15 | 2 | 0 | 0
2 | 4 | 4 | 5 | Demo top 2 or 3 (selected based on the proposals submitted) | 2016-05-01 | 2 | 0 | 0
3 | 1 | 1 | 1 | Review financial data with Sr. LMs quarterly | 2016-03-01 | 3.5 | 0 | 0
3 | 1 | 1 | 2 | Have 1st set of IDPs completed using incentive metrics | 2016-05-01 | 3.5 | 0 | 0
3 | 1 | 1 | 3 | Have 2nd pass (IDP reviews) completed & discuss progress toward goals set in first one | 2016-11-01 | 3 | 0 | 0
3 | 1 | 2 | 1 | Explore text blasting options | 2016-08-01 | 5 | 0 | 0
3 | 1 | 2 | 2 | Brainstorm ideas for next level meeting after VIP | 2016-08-01 | 5 | 0 | 0
3 | 1 | 2 | 3 | Calendar all strategic planning meetings and activities for FY18 | 2017-02-01 | 2.5 | 0 | 0
3 | 2 | 1 | 1 | Come up with safety promotions outside of work with employees and customers (picnic hard hats & safety glasses) | 2017-02-01 | 10 | 0 | 0
3 | 2 | 2 | 1 | Design and implement a four keys fanatic card | 2016-05-01 | 5 | 0 | 0
3 | 2 | 2 | 2 | Schedule Bruce Tulgan training sesssion | 2016-02-01 | 5 | 1 | 5
3 | 2 | 3 | 1 | Design incentive plan-Get with Matt after MKC Way Meeting on the 10th to fill in timelines |  | 3.5 | 0 | 0
3 | 2 | 3 | 2 | Recognize volunteers - employee newsletter |  | 3.5 | 0 | 0
3 | 2 | 3 | 3 | Involve Community Involvement |  | 3 | 0 | 0
3 | 2 | 4 | 1 | Precision ag education |  | 3.5 | 0 | 0
3 | 2 | 4 | 2 | Customer portal training |  | 3.5 | 0 | 0
3 | 2 | 4 | 3 | Train employees on new tech products and services |  | 3 | 0 | 0
3 | 3 | 1 | 1 | Define criteria and standards | 2016-04-01 | 2.5 | 0 | 0
3 | 3 | 1 | 2 | Finalize the 2016 budget | 2016-03-01 | 2.5 | 0 | 0
3 | 3 | 1 | 3 | Create baselines for each location | 2016-01-15 | 2.5 | 1 | 2.5
3 | 3 | 1 | 4 | Apply to LMs incentive program | 2016-02-28 | 2.5 | 1 | 2.5
3 | 3 | 2 | 1 | Examine development and communication scores from 2015 survey | 2015-11-01 | 2.5 | 1 | 2.5
3 | 3 | 2 | 2 | Determine date of 2016 EES | 2015-12-30 | 2.5 | 1 | 2.5
3 | 3 | 2 | 3 | Set goals for these scores and compare YOY results | 2016-08-01 | 2.5 | 0 | 0
3 | 3 | 2 | 4 | Create the target for the strategic plan scorecard | 2016-08-15 | 2.5 | 0 | 0
3 | 3 | 3 | 1 | Advertise for drivers in local retirement communities | 2015-10-15 | 3.5 | 1 | 3.5
3 | 3 | 3 | 2 | Prep flyers to recruit teachers and include instructions for distribution | 2016-04-01 | 3.5 | 0 | 0
3 | 3 | 3 | 3 | Re-advertise with retirement communities | 2016-02-01 | 3 | 0 | 0
3 | 3 | 4 | 1 | Create new questions on engagement survey | 2015-12-30 | 3.5 | 1 | 3.5
3 | 3 | 4 | 2 | Meet with 4 different focus groups (geographical) | 2016-04-01 | 3.5 | 0 | 0
3 | 3 | 4 | 3 | Examine results and create action plan for improvement | 2016-05-01 | 3 | 0 | 0
3 | 4 | 1 | 1 | Create a list of metrics | 2015-08-01 | 5 | 1 | 5
3 | 4 | 2 | 2 | Set up calendar alerts to schedule quarterly panel reviews for defined HPEs in 2016 | 2015-09-01 | 5 | 1 | 5
3 | 4 | 2 | 1 | Schedule small training sessions to ensure proper usage of IDPs using incentive objectives | 2016-03-30 | 5 | 0 | 0
3 | 4 | 2 | 2 | Incorporate management development checklist into IDP | 2016-04-01 | 5 | 0 | 0
3 | 4 | 3 | 1 | Examine job progression pathways for grain associates (asst. grain mgr) | 2016-05-01 | 5 | 0 | 0
3 | 4 | 3 | 2 | Identify necessary # of trainees by geographic location | 2016-08-01 | 5 | 1 | 5
3 | 5 | 1 | 1 | Identify company to use | 2016-03-01 | 2 | 0 | 0
3 | 5 | 1 | 2 | Which locations will host screenings | 2016-09-01 | 2 | 0 | 0
3 | 5 | 1 | 3 | Select dates for screenings | 2016-09-01 | 2 | 0 | 0
3 | 5 | 1 | 4 | Develop marketing plan using monthly managers meetings, flush flash, etc. | 2016-04-01 | 2 | 0 | 0
3 | 5 | 1 | 5 | Conduct screenings | 2016-11-01 | 2 | 0 | 0
3 | 5 | 2 | 1 | Choose quantity and type of activities | 2016-03-01 | 3.5 | 0 | 0
3 | 5 | 2 | 2 | Determine tracking method | 2016-03-01 | 3.5 | 0 | 0
3 | 5 | 2 | 3 | Compile results | 2016-12-01 | 3 | 0 | 0
3 | 5 | 3 | 1 | Choose quantity and type | 2016-03-01 | 3.5 | 0 | 0
3 | 5 | 3 | 2 | Determine tracking method | 2016-03-01 | 3.5 | 0 | 0
3 | 5 | 3 | 3 | Compile results | 2016-12-01 | 3 | 0 | 0
3 | 5 | 4 | 1 | Determine rewards | 2016-03-01 | 2 | 0 | 0
3 | 5 | 4 | 2 | Determine qualifications | 2016-03-01 | 2 | 0 | 0
3 | 5 | 4 | 3 | Determine enrollment process | 2016-03-01 | 2 | 0 | 0
3 | 5 | 4 | 4 | Execute sign up | 2016-04-01 | 2 | 0 | 0
3 | 5 | 4 | 5 | Conduct survey of participants | 2016-12-01 | 2 | 0 | 0
4 | 1 | 1 | 1 | Prepare proforma & feasability report for outright ownership | 2016-06-01 | 4 | 0 | 0
4 | 1 | 1 | 2 | Schedule a meeting & conduct comparative analysis | 2016-07-01 | 3 | 0 | 0
4 | 1 | 1 | 3 | Determine best course of action & define new tasks | 2016-08-01 | 3 | 0 | 0
4 | 1 | 2 | 1 | Create an SOP for tracking usage | 2016-04-01 | 3.5 | 0 | 0
4 | 1 | 2 | 2 | Set up meetings with users to discuss functionality | 2016-07-01 | 3.5 | 0 | 0
4 | 1 | 2 | 3 | Decide on a reporting method to measure effectiveness | 2017-02-01 | 3 | 0 | 0
4 | 2 | 1 | 1 | Get with Matt on phase 1 & 2 dashboard development tasks and timelines |  | 10 | 0 | 0
4 | 2 | 2 | 1 | Educate and train on process |  | 5 | 0 | 0
4 | 2 | 2 | 2 | Apply to current projects |  | 5 | 0 | 0
4 | 2 | 3 | 1 | Get with Matt about tasks and timelines for annual plan to review ERP system |  | 10 | 0 | 0
4 | 2 | 4 | 1 | Get with Matt about task and timelines for grain software program |  | 10 | 0 | 0
4 | 3 | 1 | 1 | Make a list of locations | 2016-04-01 | 5 | 0 | 0
4 | 3 | 1 | 2 | Prioritize actions for each location and present to BOD | 2016-06-01 | 5 | 0 | 0
4 | 3 | 2 | 1 | Make a task for each location and timeline them | 2017-02-01 | 10 | 0 | 0
4 | 4 | 1 | 1 | Prepare for zoning hearing | 2016-03-02 | 3.5 | 0 | 0
4 | 4 | 1 | 2 | Approval pending 2 weeks later | 2016-03-21 | 3.5 | 0 | 0
4 | 4 | 1 | 3 | IRB discussion to follow | 2016-04-01 | 3 | 0 | 0
4 | 4 | 2 | 1 | Prepare facility design for IRB meeting | 2016-03-01 | 10 | 1 | 10
4 | 4 | 3 | 1 | Outline critical dates for news releases | 2016-03-01 | 10 | 1 | 10
4 | 4 | 4 | 1 | Design ideal grain operations | 2016-08-01 | 2.5 | 0 | 0
4 | 4 | 4 | 2 | Outline details of all agronomy departments (Seed, CPP, CN, Application services, Precision ag) | 2016-08-01 | 2.5 | 0 | 0
4 | 4 | 4 | 3 | Define all risk management offerings | 2016-08-01 | 2.5 | 0 | 0
4 | 4 | 4 | 4 | Decide upon size of energy operations | 2016-08-01 | 2.5 | 0 | 0
4 | 4 | 5 | 1 | Prepare HR model draft for IRB meeting-FT & PT | 2016-04-01 | 3.5 | 0 | 0
4 | 4 | 5 | 2 | Organize job fair | 2016-08-01 | 3.5 | 0 | 0
4 | 4 | 5 | 3 | Start training schedules | 2016-08-01 | 3 | 0 | 0
4 | 5 | 1 | 1 | Get with Dave Spears about tasks that will drive these actions |  | 10 | 0 | 0
4 | 5 | 2 | 1 | Get with Dave Spears about tasks that will drive these actions |  |  |  | 0
4 | 6 | 1 | 1 | Pending decision | 2016-04-01 | 10 | 0 | 0
4 | 6 | 2 | 1 | Pending decision | 2016-04-01 | 10 | 0 | 0

## Initiatives FY16
PID | INID | Description | Progress | notes
1 | 1 | Identify key market growth areas | 12.5 | A potential merger partner list with contacts and notes is reviewed and updated every 2 weeks by Darin. (Attach example?) Prospective partnerships with independent retailers are also logged and updated here. The large project list has been updated and prioritized for 2016/17 and is now scheduled to be reviewed quarterly to capture changes and additions in real time. (Attach example?) An alert has been established to revisit the identification of potential green field sites every 6 months with Dave C. and Ted.
1 | 2 | Expense management | 0 | A financial dashboard is currently being created to house location specific sales and expense items by month for key employees to be able to review monthly. IT is troubleshooting the source and flow of data to ensure accuracy and timeliness. Still on pace for a February roll out. Training piece will follow on how to navigate and evaluate the content. *Consider adding an action for monthly variance reporting to encourage usage, understanding, accountability and to measure baseline performance standards. The Margin/Expense Management Committee is established and currently prioritizing cost saving projects, (Attach example?), and finding ways to measure success of each one including BuyPoint which is still in the feasibility phase.
1 | 3 | Board Initiative - Explore criteria for voting membership | #REF! | Other methods have been identified to compare and contrast. No changes are currently being made but next steps have been identified for preparedness including feasibility reporting to the BOD, reviewing bylaws, and meeting with governance committee for in-depth evaluation.
1 | 4 | Telling the MKC story to merger candidates' board members and employees | #REF! | New talking points were created when designing the Initiative In Review for Telling the MKC Story. (Attach example?) Dave C. reviewed these talking points in the November 2015 Monthly Manager Meeting. These talking points were included in December's Team Meeting Agenda to review with entire employee group. A Board Committee has been identified to champion merger candidate meetings & presentations. BOD development sessions are scheduled in Jan & Mar of 2016 to keep momentum in continuing education. *Consider adding new action to include customer testimonial videos.
2 | 1 | Maximize sales performance | 43 | Share of wallet continues to drive sales efforts. Measurements have been established as: 60% + share of wallet per business unit = existing customer, 21%-59% = targeted customer and > 20% = prospective customer. A better & more accurate forecasting tool is up for discussion in Q1 in order to tie to incentive plans appropriately. 2 MAA's have been hired. *Consider adding new actions here regarding MAA smart goals and define 3MIL account strategy. The execution of the CFA marketing plan was proven successful by exceeding the original goal by 48 loans. This is a 46% increase over LY. We are currently testing CRM's capability in generating a priority account report every Monday that pulls accounts that have exceeded their departmentally determined, acceptable length of time without contact. Should go live in FEB. The strategy to capture 15 new 1MIL accounts is underway and on pace with 60 identified targets (Attach list?). Checkpoints are scheduled in Q2 to narrow the focus and discuss capture strategy. War boards, (Attach example?), have been implemented to track and identify Field Marketer goals and pace to goals for inputs and application each month.
2 | 2 | Enhance customer experience | 16.25 | Relationship with LOL was leveraged to create and successfully launch the new MKC website on January 14th 2016. (Attach link?) Phase one is complete with continued troubleshooting behind the scenes to include enhancements such as depth of organization with employee bios highlighting the youth and expertise of our leadership group. Phase two will include customer log in components, membership materials and career page enhancements. *Consider adding new action items after receiving phase 2 milestones from LOL. Please note, the YouTube videos to assist in navigating the customer portal will be recorded after phase two to capture most current functionality. In reference to implementing customer face to face reviews, it has been determined to utilize CRM's Power Survey module to house the survey questions. Power Survey will be tested on the employee group first before rolling out to customers. An April deadline has been defined to have administered a survey to at least the top 10 accounts. Survey questions (Attach questions?) will be customized for Agronomy services, Grain services, and Energy Services. All of which will be launched strategically by season. Agronomy after fall harvest and Grain after wheat harvest. Energy TBD. Power Survey will also be used to measure specific customer experiences after services or loan fulfillments. It has been determined that customer engagement can be measured by 3 things: 60% share of wallet, 20% service surveys, and 20% of meeting or event attendance currently being tracked by Power Zap Event via CRM. Regarding SOP development, all recorded processes have been transferred to the new template via summer interns (Attach SOP template?). *Consider new action item to audit department files to identify any critical procedures without a formal SOP. Lastly, regarding customer prepay contracts; seed and chemical contracts are done. Fertilizer will not change and Energy is underway but stalled for now. *Consider new action to include formal training and/or checkpoints to determine if new contracts are working as planned.
2 | 3 | Develop strategies to target gaining business with farmers under 40 years old | 25 | Sales training to include multigenerational selling techniques will be included in the FLM+ training series. As soon as this piece is incorporated into the curriculum, we will determine how to measure its effectiveness. Generational speaker Bruce Talgan is scheduled for employee groups in January. A special list of invitees was compiled to target Sumner County young producers to attend EPP. Individual follow up calls to these participants is underway. Written survey and instant click survey results have been complied and reviewed by champion group. We are still in the discovery phase for building appropriate benchmarks for farmers under 40. FBN software is still being considered.
2 | 4 | Enhance precision ag strategy | 66.6667 | New website content is live and very well represented. We are still in the approval process with the FAA for our UAV but are currently compiling a list of prospective services to add to our precision ag portfolio upon this approval. Customer education meetings are being planned now for 2016. *Consider new actions to include defining new marketing strategies to drive precision ag services and how this will affect the new sales incentive.
3 | 1 | Communicate the strategic plan to employee group & incorporate into their performance plan | 0 | We are currently showcasing one initiative in review (Attach example?) each month in the monthly manager's meeting consisting of a brief presentation from the champion on how to carry the message over into location team meetings as outlined in the new company wide agenda. (Attach example?) We are leveraging the outreach of the employee newsletter as well and including an initiative article in each edition, relative to what was reviewed that month in their team meetings. (Attach example?). Each review is housed in the M-drive for access and reference when discussing performance plans to determine which initiative or action may resonate with that employee for future mentoring. VIP Meetings have been introduced will occur annually. *Consider adding an action to dive deeper into the employee group with the assistance of VIPs to administer location level strategic planning.
3 | 2 | Living the Four Keys: Safety, Courtesy, Image and Innovation | 12.5 | Safety messages are distributed every Monday by a Safety Committee member. Prescription eye protection, Driver training, and Hot work permits have all been successfully implemented. A more consistent platform for daily safety meetings is currently in review. Location safety audits are underway for 2016 with a goal to have all of them complete by Q2. Accidents are being investigated as they happen and information is being shared at the start of every meeting. *Consider adding an action relative to the proposal for a safety data warehouse. Courtesy tactics currently in place include the monthly customer service topic as well as the incorporation of the 4 keys in the company wide agenda for each location's monthly team meeting. The image audit template has been redesigned and the SOP is in place. Audits are currently underway by the MKC Way Committee. Innovative solutions are being recognized in monthly manager meetings. The MKC Way Committee has created a checklist to monitor submissions and ensure follow through. Standards for incentives are being written now.
3 | 3 | Employee engagement | 34 | The OT & Wage Study are complete with no indication that our ratios and averages are anywhere outside the competitive set. Financial performance standards have been determined for each location and will roll into the new incentive program as scheduled. The Employee Engagement Survey (EES) is scheduled for 2016 and with those results a YOY comparison will determine targets for the 2017 strategic plan with emphasis on employee development and communications. Advertisements for drivers have been posted at local retirement communities to increase peak time workforce needs as well as tapping into other cooperatives' workforces that are on opposite seasons. The Expense/Margin Management Committee conducted a cost analysis on temp/PT vs. FT employees and found favorable results toward FT employment. H-2A Visas have been investigated as well and found to be an undesirable source for seasonal help. Sub surveys will launch after the EES to analyze employee's ideas on quality of life. Geographically selected employee focus groups will also be assembled to gain understanding and create action items toward improvement in Q2.
3 | 4 | Employee development | 30 | Applicator training checklist is developed and currently being revised to accommodate soft skills and 30-60-90 day checkpoints. *Consider adding action to create the SOP and roll out company wide. HPE metrics have been defined and a panel review will be scheduled to discuss HPEs on the list. The first pass on an IDP template was released for review in January. *Consider new actions to drive training to LMs on how to administer IDPs and mentor HPEs. Flyers are being designed to recruit teachers to include instructions on how and where to distribute these flyers. Recruiting efforts for Cloud County program are complete and FLM+ Sales training is underway.
3 | 5 | Drive employee wellness | 0 | *Consider adding new actions to drive the examination of the wellness requirements for the new benefits package.
4 | 1 | Evaluate logistics effectiveness/efficiency | 0 | Proformas and feasibility reports for outright fleet ownership are complete. Meetings are scheduled to occur in Q1 2016 to conduct comparative analysis and determine the best course of action. Razor tracking is fully implemented. *Consider adding new actions that investigate complete functionality.
4 | 2 | Continue to identify software platform enhancements | 0 | A Manager of Applications Development was hired in June 2016. The decision to move forward with Logi has led IT toward more rapid completion of critical dashboards including this one. (Attach project list?)
4 | 3 | Establish education and control measures for grain handling employees | 0 | The scorecard template is complete (Attach example?). Grain quality grades have been determined. Waiting on financial dashboards for locations to examine results and apply to new incentive program.
4 | 4 | Analyze feed operations to optimize performance | 50 | Options have been identified for more review.
…………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….
-

## Actions FY16
PID | INID | ACTID | Description | Champion | Team | Due Date | Progress | Notes
1 | 1 | 1 | Continue discussion with potential cooperative merger partners | Darin | Dave & Senior Leadership Team | ongoing | 50 | Have 25 discussions in progress. Will develop strategies to communicate message to Directors. Will organize meetings with large, strategic producers in Sumner County region.
1 | 1 | 2 | Evaluate existing property upgrades to drive market growth | Jon | Darin, Erik, Steve, Dave S. | ongoing | 0 | A list is active and updated every 6 months to capture additions and changes. They are prioritized by urgency and grouped by large and small projects.
1 | 1 | 3 | Identify locations for potential greenfield sites | Dave | Ted | ongoing | 0 | Several have been identified.
1 | 1 | 4 | Investigate M&A or partnerships with independent retailers | Dave | Darin, Erik, Steve, Dave S. | ongoing | #REF! | A list is started with emphasis on fertilizer/grain retailer in eastern KS.
1 | 2 | 1 | Training on Expense Management Initiatives for key employees | Vice Presidents of Operations | Vice Presidents of Operations | 2016-02-01 | 0 | Financial dashboards are in development. Monthly ratios are currently being shared with key employees to increase exposure to location specific financial data.
1 | 2 | 2 | Investigate the value of total margin/expense management | Chris | John | 2017-02-01 | 0 | Committee is meeting on a regular basis. They are identifying quality, cost saving projects.
1 | 3 | 1 | Investigate other methods | Dave |  | 2016-02-01 | #REF! | Proposal has been brought to the Board examining business over the past 2 years.
1 | 3 | 2 | Review bylaws for feasibility | Dave |  | 2016-02-01 | #REF! | Next steps for preparedness are in progress. Legal counsel has provided guidance that this will be a Director Policy change.
1 | 4 | 1 | Provide talking points and other materials to be used in education and relationship-building meetings | Nichole | Executive Team, Communications | 2015-12-01 | #REF! | Talking points are created and saved in the M-drive under Strategic Planning. Sumner County points are drafted.
1 | 4 | 2 | Provide Board Members development opportunities to educate candidates' Board Members | Dave | Nichole | 2016-02-01 | #REF! | BOD development sessions are scheduled annually to keep momentum in continuing education.
1 | 4 | 3 | Develop a Board Committee that is responsible for meetings, presentations and education of merger candidates' board members | Dave | Board of Directors | 2016-02-01 | #REF!
2 | 1 | 1 | Refine forecasting process to measure variances and tie to incentive | Kent | Dave S., Willie | 2016-09-01 | 30 | Expanded beyond Field Marketers to involve all agronomy hubs. Incentives are currently being developed and on pace for September.
2 | 1 | 2 | Hire Master Agronomy Advisor | Dave S. |  | ongoing | 25 | Complete.
2 | 1 | 3 | Develop a marketing campaign for CFA with a goal of 75 new loans | Dave S. | Nichole, Kent, Tim B. | 2016-02-01 | 75 | Added 123 new loans, 46% increase over LY. Increased loan commitments 13 MIL. Utilization is 30% measured in calendar year. Multiple marketing campaigns tied to CFA.
2 | 1 | 4 | Incorporate CRM functionality to highlight priority accounts | Kent | Devin, Matt | 2015-12-01 | 50 | Currently testing the CRM module and will roll out and train by FEB.
2 | 1 | 5 | Identify and launch strategy to capture 15 new, $1 million, combined business unit accounts | Dave S. | Willie, Kent, Devin | 2016-09-01 | 35 | 60 accounts have been identified and assigned to Field Marketers, MAAs, and Grain Marketers.
2 | 2 | 1 | Meeting with Land O'Lakes to define MKC needs for customer portal | Matt | Dave S., Devin, Nichole, Willie, Kent | 2015-09-01 | 0 | Complete. Met with LOL in several planning sessions to determine needs and put together a phase approach to the portal project.
2 | 2 | 2 | Phase I Completion - Main current MKC website replacement | Matt | Dave S., Devin, Nichole, Willie, Kent | 2016-03-01 | 60 | Complete. New website is launched fulfilling phase 1.
2 | 2 | 3 | Investigate online membership application, credit app, new customer packet, etc. | Matt |  | 2015-11-01 | 20 | Researched software options with LOL that will integrate with new MKC portal.
2 | 2 | 4 | Implement annual customer experience face-to-face reviews with targeted accounts | Willie | Kent, Devin, Dave S. | 2016-12-01 | 0 | Universal questions for the review are complete. Survey will launch through CRM. Top 10 accounts for each Field Marketer time-lined to complete by APR 1.
2 | 2 | 5 | Identify methodology to measure customer experience | Nichole | Devin, Willie, Kent, MKC Wat | 2015-12-01 | 50 | CRM will launch surveys. Calendar is created for surveys to conduct throughout the year. Questions are being finalized.
2 | 2 | 6 | Establish YouTube video and hold training sessions for basic navigation of existing customer portal | Nichole | Brett, Steve, Erik, Darin | 2015-11-01 | 0 | Phase 1 completion of the website is driving timeline for video. Scripts are ready. Field Staff will be trained and Champions identified for each location.
2 | 2 | 7 | Continue SOP development, maintenance and management of the process | Nichole | SOP Committee | 2016-01-01 | 0 | Complete. The Committee has completed organization by department in the M-drive and SOP is active. Champions are identified for each department to maintain consistency and updates. Committee will investigate options for distribution.
2 | 2 | 8 | Roll out changes to customer pre-pay input contracts | Danny | Willie, Kent, Dave S., Dave S. | 2015-10-15 | 0 | Changes are made to seed and CPP contracts. Training is complete. Fertilizer will not change at this time. Energy is in progress and pending changes based on access to sales contract module.
2 | 3 | 1 | Sales training to include multi-generational selling | Willie | Devin, Kent | ongoing | 0 | 3rd annual EPP successful. FLM+ sales training will include generational selling topic in curriculum starting in FEB. Guest speaker, Bruce Tulgan is scheduled for sessions in FEB specifically covering differences in generations.
2 | 3 | 2 | Invite 4 growers from targeted geography to Emerging Producers Program with follow-up discussions afterward | Willie | Nichole, Devin, Kent | ongoing | 0 | 6 growers in attendance. Follow up are in progress.
2 | 3 | 3 | Build Benchmarks from focus group and create S.O.P.s | Willie | Dave S., Kent, Devin, Erik | 2015-12-01 | 75 | Continuing to review software partners to provide benchmarking and business alignment with MKC.
2 | 3 | 4 | Develop metrics to measure success of Emerging Producers Program through CRM | Kent | Nichole, Willie, Devin | 2016-05-01 | 25 | All of the EPP invitees are tracked in CRM. Exploring whether CRM will build the reports or if MKC will build internally.
2 | 4 | 1 | Improve website content | Ross | Craig, Dave S., Nichole | 2016-03-01 | 70 | New website content is updated with enhancements to come.
2 | 4 | 2 | Investigate potential services from UAV licensing | Ross | Craig, Dave S., GPPA | 2016-09-01 | 65 | Awaiting section 333 commercial exemption license. Services will launch thereafter.
2 | 4 | 3 | Conduct 6-8 precision ag educational meetings with customers | Ross | Craig | 2016-03-01 | 65 | 3 are complete and 5 more are scheduled to complete by FEB.
3 | 1 | 1 | Vice Presidents and Division Managers to overview outcomes of strategic planning twice per year | Amy | VPs, DMs | ongoing | 0 | Strategic Recap Meeting is scheduled in March and a new process of consistently reviewing an Initiative in Review by each Lead Champion in Monthly Manager's Meetings has been adopted.
3 | 1 | 2 | Create a company-wide monthly agenda for what will be communicated | Amy | Executive Team, Communications | ongoing | 0 | Complete. New template is being used in each location's Monthly Team Meetings and contains consistent messaging for the Initiative in Review.
3 | 1 | 3 | Utilize other communication methods to carry message (employee newsletter, employee portal, meeting notes, monthly employee meetings) | Amy | Nichole, Matt, Location Managers | ongoing | 0 | We are leveraging the reach of the employee newsletter and incorporating an Initiative article each month. Initiatives in Review are housed in the M-drive and are distributed with the Monthly Team Meeting Agendas.
3 | 2 | 1 | Task Safety Committee to develop methods to lower Workman's Comp rate to 0.80% or less | Jeff | Safety Committee | annually | 50 | Daily safety meetings are in progress. There is a safety article in each employee newsletter. There is a new accident investigation process and annual Nationwide training sessions and agronomy safety sessions are scheduled.
3 | 2 | 2 | Design motivational tactics to encourage courtesy |  | MKC Way Committee | 2016-02-01 | 0 | Utilize monthly customer service topics to review in each location's team meetings. Team meeting review of Courtesy is scheduled 3x year.
3 | 2 | 3 | Continue the image audits |  | MKC Way Committee | 2016-02-01 | 0 | Redesigned image audit template and SOP. Image audits are done 2X year in March and September.
3 | 2 | 4 | Celebrate innovation solutions awards |  | MKC Way Committee | 2016-02-01 | 0 | Celebrated in Monthly Manager Meetings. Created a sub committee of MKC alumni to ensure standards for incentives are followed.
3 | 3 | 1 | Conduct an overtime/wages study | Brett | Jeff | 2015-09-01 | 0 | Complete. Year 2 analysis is underway. Compared to LOL peers, we are in alignment with industry standards.
3 | 3 | 2 | Set standards per location to be rolled into the new incentive program | Danny | Erik, Steve, Darin, Dave S. | 2016-02-01 | 50 | Initial incentive measurements have been established. Company standards are in place with location specific standards to follow.
3 | 3 | 3 | Develop hard targets for development and communication using the engagement survey results | Brett | Jeff | 2016-02-01 | 0 | ES will be completed EOM February. Data analysis will follow and targets will be developed from those results.
3 | 3 | 4 | Investigate opportunities to improve peak-time workforce needs | Brett | Jeff | 2016-02-01 | 0 | Newspaper ads are current. Ads will be posted in Bluestem retirement community newsletters.
3 | 3 | 5 | Investigate opportunities to measure employee quality of life | Brett | Jeff | 2016-02-01 | 0 | Adding 2 new questions to ES specifically to measure quality of life. Results may indicate a better method to match job descriptions to employee's desired measurements.
3 | 4 | 1 | Develop Applicator Training | Brett |  | 2016-02-01 | 0 | Complete. Requires additional feedback from Managers and will organize roll out to meet timeline.
3 | 4 | 2 | Utilize metrics to define HPE's and conduct panel review with executive team | Brett | Sr Mgmt | 2015-09-01 | 0 | metrics are defined. Panel review will be scheduled to review current list of HPEs.
3 | 4 | 3 | Design PDPs for high potential employees | Brett | Jeff, Sr Mgmt | 2016-02-01 | 100 | PDP form is approved. IDPs for HPEs to be reviewed in MAR/APR.
3 | 4 | 4 | Increase bench-strength and develop pool of seasonal part-time help | Jeff | Brett, Steve, Erik, Darin | 2016-02-01 | 200 | Assistant Field Marketer and Assistant Agronomy Ops programs very successful. 30%+ of interns are permanently hired after participating in internship program.
3 | 4 | 5 | Create a management development program | Brett |  | 2016-02-01 | 200 | Checklist is developed and will connect to IDPs.
3 | 5 | 1 | Investigate potential wellness providers | Hillary | Wellness Committee | 2016-05-01 | 0 | Complete. Have investigated provider options. With current benefit changes, we will manage our own wellness plan while utilizing and current provider tools.
4 | 1 | 1 | Continue to investigate fleet ownership feasibility versus the lease/hire option | Erik | Steve, Dave Sell, Doug, John W., Ted | ongoing | 0 | Performa is developed and TMA is reviewing it for ownership. Opportunities for improvement include back hauling fertilizer. Utilizing MKC fleet and drivers to haul TMA commodities when available. Additional planning sessions are being scheduled.
4 | 1 | 2 | Compile optimal usage and functionality of Razor Tracking | Erik | Matt, Steve, Dave Sell, Doug, John W., Ted | tied to 411 | 0 | Razor tracking almost 100% installed and being utilized. Data is being collected. Software changes will enhance functionality. SOP pending final draft. Currently exploring new uses for razor tracking.
4 | 2 | 1 | Hire a Manager of Applications Development | Matt | Matt | 2015-09-15 | 0 | Complete.
4 | 2 | 2 | Identify and complete remaining Business Intelligence and Dashboards | Matt | Danny, Tricia | ongoing | 0 | Purchased dashboard/analytic software platform. Identified key dashboards for MKC and TMA and broke them down in 2 phases for completion.
4 | 3 | 1 | Incorporate managers'/superintendents' scorecard into incentive program | Brett | Steve, Erik, Jeff, Darin | 2016-02-01 | 0 | Complete. Grain quality scorecards are incorporated into new incentive program.
4 | 4 | 1 | Explore various Feed operations structures | Dave | Erik, Darin, Steve | 2016-02-01 | 200 | Scenarios have been identified.
4 | 4 | 2 | Develop a plan to present to the Board of Directors | Dave | Erik, Darin, Steve | 2016-02-01 | 0 | More to come.

## Tasks FY16
PID | INID | ACTID | TASKID | Description | Due Date | Weight | Complete | Measure
1 | 1 | 1 | 1 | Create spreadsheet with all active & prospective discussions | 2015-10-05 | 5 | 1 | 5
1 | 1 | 1 | 2 | Email spreadsheet to Darin 2 times a month to update and file | 2015-10-31 | 5 | 1 | 5
1 | 1 | 2 | 1 | Update large project list | 2015-11-11 | 5 | 1 | 5
1 | 1 | 2 | 2 | Revisit after staff meetings every other month | 2015-12-15 | 5 | 1 | 5
1 | 1 | 3 | 1 | Identify 5-6 targets | 2015-08-25 | 5 | 1 | 5
1 | 1 | 3 | 2 | Send email alert to check progress on each every 6 months | 2015-12-15 | 5 | 1 | 5
1 | 1 | 4 | 1 | Add prospective independent retailers to merger discussion spreadsheet | 2015-10-08 | 5 | 1 | 5
1 | 1 | 4 | 2 | Email spreadsheet to Darin 2 times a month to update and file | 2015-12-15 | 5 | 1 | 5
1 | 2 | 1 | 1 | Create location specific financial reports | 2015-12-14 | 3.5 | 0 | 0
1 | 2 | 1 | 2 | Set meeting to discuss critical expense items to include on training checklist | 2016-01-20 | 3.5 | 0 | 0
1 | 2 | 1 | 3 | Finalize training checklist and present in monthly manager meeting | 2016-02-24 | 3 | 0 | 0
1 | 2 | 2 | 1 | Create Committee | 2015-06-11 | 2.5 | 1 | 2.5
1 | 2 | 2 | 2 | Prepare list of savings projects and prioritize by most $ saved | 2015-11-01 | 2.5 | 1 | 2.5
1 | 2 | 2 | 3 | Find ways to measure success of each project | 2015-12-31 | 2.5 | 0 | 0
1 | 2 | 2 | 4 | Define projects for FY 2016 and timeline them | 2016-03-01 | 2.5 | 0 | 0
1 | 3 | 1 | 1 | Set reminder email for Dave end of Q4 2015 | 2015-10-23 | 3.5 | 1 | 3.5
1 | 3 | 1 | 2 | Identify 2 other methods to compare to and draw up SWOTs | 2016-01-08 | 3.5 | 1 | 3.5
1 | 3 | 1 | 3 | Present results of feasability in BOD meeting | 2016-02-18 | 3 | 1 | 3
1 | 3 | 2 | 1 | Arrange meeting with Danny to review bylaws | 2016-02-05 | 3.5 | 1 | 3.5
1 | 3 | 2 | 2 | Arrange meeting with legal counsel to review bylaws | 2016-01-30 | 3.5 | 1 | 3.5
1 | 3 | 2 | 3 | Prepare report for BOD meeting | 2016-02-11 | 3 | 0 | 0
1 | 4 | 1 | 1
1 | 4 | 1 | 2 | Create talking points for employees to use moving forward | 2015-11-01 | 5 | 1 | 5
1 | 4 | 1 | 3 | Present in monthly manager meeting to review in team meetings | 2015-12-01 | 5 | 1 | 5
1 | 4 | 2 | 1 | Explore board of directors development programs | 2015-10-01 | 3.5 | 1 | 3.5
1 | 4 | 2 | 2 | Confirm date and time for training session | 2015-10-15 | 3.5 | 1 | 3.5
1 | 4 | 2 | 3 | Survey BOD for feedback on the session | 2016-04-14 | 3 | 0 | 0
1 | 4 | 3 | 1 | Discuss forming a committee with BOD | 2015-09-01 | 3.5 | 1 | 3.5
1 | 4 | 3 | 2 | Consider utilizing executive team | 2015-10-01 | 3.5 | 1 | 3.5
1 | 4 | 3 | 3 | Make a decision | 2016-02-01 | 3 | 1 | 3
2 | 1 | 1 | 1 | Discuss the methodology to forecast properly | 2016-02-01 | 3 | 1 | 3
2 | 1 | 1 | 2 | Build a better forecasting tool | 2016-04-01 | 3.5 | 0 | 0
2 | 1 | 1 | 3 | Tie it to incentive plan | 2016-09-01 | 3.5 | 0 | 0
2 | 1 | 2 | 1 | Hire Master Agronomy Advisor | 2015-11-30 | 10 | 1 | 10
2 | 1 | 3 | 1 | Push out CFA Postcards | 2015-10-30 | 2.5 | 1 | 2.5
2 | 1 | 3 | 2 | Create a target list and present to Dave Spears | 2015-11-30 | 2.5 | 1 | 2.5
2 | 1 | 3 | 3 | Complete all 1 on 1 visits with Field Marketers | 2015-12-31 | 2.5 | 1 | 2.5
2 | 1 | 3 | 4 | Progress report on all new CFA loans to Dave Spears | 2016-01-30 | 2.5 | 1 | 2.5
2 | 1 | 4 | 1 | Sign integration agreement with PowerObjects | 2015-11-01 | 2.5 | 1 | 2.5
2 | 1 | 4 | 2 | Define acceptable length of days with no contact | 2015-11-15 | 2.5 | 1 | 2.5
2 | 1 | 4 | 3 | Create alerts to push out every Monday to Field Marketers | 2015-12-10 | 2.5 | 0 | 0
2 | 1 | 4 | 4 | Create report to send out to Managers once a month | 2015-12-30 | 2.5 | 0 | 0
2 | 1 | 5 | 1 | Willie and Kent provide Dave Spears a list of targeted growth accounts | 2015-12-01 | 3.5 | 1 | 3.5
2 | 1 | 5 | 2 | Willie and Kent checkpoint with Dave Spears | 2016-04-30 | 3 | 0 | 0
2 | 1 | 5 | 3 | Willie and Kent continue go to market strategy | 2016-08-31 | 3.5 | 0 | 0
2 | 2 | 1 | 1 | Invite LOL to Groveland for a meeting | 2015-08-28 | 5 | 1 | 5
2 | 2 | 1 | 2 | Follow up with LOL and receive milestone timeline | 2015-09-30 | 5 | 1 | 5
2 | 2 | 2 | 1 | Redesigned website | 2016-01-14 | 10 | 1 | 10
2 | 2 | 2 | 2
2 | 2 | 2 | 3
2 | 2 | 3 | 1 | Investigation | 2016-09-15 | 10 | 1 | 10
2 | 2 | 4 | 1 | Choose method to administer review; possibly CRM | 2015-11-01 | 2.5 | 1 | 2.5
2 | 2 | 4 | 2 | Come up with 7 universal questions | 2015-12-15 | 2.5 | 1 | 2.5
2 | 2 | 4 | 3 | Define accounts and schedule reviews | 2016-01-30 | 2.5 | 1 | 2.5
2 | 2 | 4 | 4 | Collect data and create action plans for Field Marketers | 2016-03-30 | 2.5 | 0 | 0
2 | 2 | 5 | 1 | Investigate CRM capabilities | 2015-11-01 | 3.5 | 1 | 3.5
2 | 2 | 5 | 2 | Define measures of engagement | 2015-11-15 | 3 | 1 | 3
2 | 2 | 5 | 3 | Have a survey meeting to define types and targets | 2015-11-20 | 3.5 | 1 | 3.5
2 | 2 | 6 | 1 | Meet with IT to understand portal modules | 2015-10-10 | 2.5 | 1 | 2.5
2 | 2 | 6 | 2 | Map and script the content | 2015-10-30 | 2.5 | 1 | 2.5
2 | 2 | 6 | 3 | Troubleshoot the flow | 2015-11-30 | 2.5 | 1 | 2.5
2 | 2 | 6 | 4 | Record final version and set up training schedule | 2015-12-30 | 2.5 | 0 | 0
2 | 2 | 7 | 1 | Create SOP Committee and choose SOP template | 2015-01-30 | 3.5 | 1 | 3.5
2 | 2 | 7 | 2 | Begin process transfers into new template | 2015-02-01 | 3.5 | 1 | 3.5
2 | 2 | 7 | 3 | Continue to transfer processes; last count 106 | 2015-11-30 | 3 | 1 | 3
2 | 2 | 8 | 1 | Decide upon 4 new types of pre-pay contracts | 2015-08-10 | 1 | 1 | 1
2 | 2 | 8 | 2 | Go through due diligence for each one | 2015-09-30 | 2 | 1 | 2
2 | 2 | 8 | 3 | Have seed & fertilizer contracts complete | 2015-10-15 | 1 | 1 | 1
2 | 2 | 8 | 4 | Have energy and CP contracts complete | 2015-12-15 | 2 | 1 | 2
2 | 2 | 8 | 5 | Lawyer assessments and approvals for all contracts (energy pending) | 2015-12-30 | 2 | 0 | 0
2 | 2 | 8 | 6 | Formal training for key employees on all contracts (energy pending) | 2016-01-30 | 2 | 0 | 0
2 | 3 | 1 | 1 | Determine source and curriculum for training | 2015-09-01 | 2.5 | 1 | 2.5
2 | 3 | 1 | 2 | Acquire training schedule through FLM+ | 2015-10-01 | 2.5 | 1 | 2.5
2 | 3 | 1 | 3 | Discuss effectiveness of administration of topic | 2016-02-28 | 2.5 | 0 | 0
2 | 3 | 1 | 4 | Consider guest speakers to enhance effectiveness | 2016-01-15 | 2.5 | 1 | 2.5
2 | 3 | 2 | 1 | Compile list of invitees to include Sumner County | 2015-11-15 | 2.5 | 1 | 2.5
2 | 3 | 2 | 2 | Send out invitations | 2015-11-30 | 2.5 | 1 | 2.5
2 | 3 | 2 | 3 | Ensure Field Marketers made invitational follow up calls | 2015-12-01 | 2.5 | 1 | 2.5
2 | 3 | 2 | 4 | Set up internal meeting to discuss info collected from follow up | 2016-01-29 | 2.5 | 1 | 2.5
2 | 3 | 3 | 1 | Consider FBN software | 2015-11-01 | 3 | 1 | 3
2 | 3 | 3 | 2 | Run a pilot on a few producers and collect data | 2015-12-15 | 3.5 | 1 | 3.5
2 | 3 | 3 | 3 | Set up a meeting to discuss results and how to move forward | 2015-12-30 | 3.5 | 1 | 3.5
2 | 3 | 4 | 1 | Create survey questions to launch after EPP | 2016-01-10 | 2.5 | 1 | 2.5
2 | 3 | 4 | 2 | Launch through CRM | 2016-01-22 | 2.5 | 0 | 0
2 | 3 | 4 | 3 | Discuss results and log changes for next year | 2016-03-01 | 2.5 | 0 | 0
2 | 3 | 4 | 4 | Begin planning EPP 2017 | 2016-05-01 | 2.5 | 1 | 2.5
2 | 4 | 1 | 1 | Provide LOL current precision ag data for Phase 1 | 2015-09-30 | 3.5 | 1 | 3.5
2 | 4 | 1 | 2 | Continue to collect new content & ideas to prepare for updates | 2016-02-15 | 3.5 | 1 | 3.5
2 | 4 | 1 | 3 | Evaluate new website and update as necessary | 2016-03-30 | 3 | 0 | 0
2 | 4 | 2 | 1 | Submit for UAV licensing | 2016-01-30 | 3 | 1 | 3
2 | 4 | 2 | 2 | Make a list of services offered or intended to offer | 2016-02-28 | 3.5 | 1 | 3.5
2 | 4 | 2 | 3 | Discuss marketing options for selected UAV services | 2016-04-01 | 3.5 | 0 | 0
2 | 4 | 3 | 1 | Prepare a schedule with dates, times & locations for new year | 2015-12-05 | 3 | 1 | 3
2 | 4 | 3 | 2 | Discuss marketing collateral needs and timelines | 2015-12-30 | 3.5 | 1 | 3.5
2 | 4 | 3 | 3 | Collect information from customers & discuss results in Monthly Managers meetings | 2016-03-30 | 3.5 | 0 | 0
3 | 1 | 1 | 1 | Schedule dates for planning sessions (Aug & Jan) | 2015-06-01 | 3.5 | 1 | 3.5
3 | 1 | 1 | 2 | Schedule date for recap @ monthly manager meeting (March) | 2015-09-01 | 3.5 | 1 | 3.5
3 | 1 | 1 | 3 | Schedule date for VIP meeting (Dec) | 2015-11-11 | 3 | 1 | 3
3 | 1 | 2 | 1 | Create a schedule & review template for each initiative to cover 1 in every monthly manager's meeting | 2015-08-30 | 3.5 | 1 | 3.5
3 | 1 | 2 | 2 | Create universal team meeting agenda template to include above intiatives in review | 2015-09-30 | 3.5 | 1 | 3.5
3 | 1 | 2 | 3 | Create a synopsis of each initiative including interactive talking points | 2015-12-30 | 3 | 1 | 3
3 | 1 | 3 | 1 | Publish a newsletter article relative to the initiatives in review monthly | 2015-12-30 | 2.5 | 1 | 2.5
3 | 1 | 3 | 2 | Put initiatives in review on M-Drive for all user access | 2015-12-30 | 2.5 | 1 | 2.5
3 | 1 | 3 | 3 | Visit 3-4 team meetings/month to ensure consistency | 2015-12-30 | 2.5 | 1 | 2.5
3 | 1 | 3 | 4 | Ensure Champions are prepared to present intiatives in review at monthly manager's meetings | 2015-12-30 | 2.5 | 1 | 2.5
3 | 2 | 1 | 1 | Create weekly safety messages and distribute every Monday | 2015-02-01 | 1 | 1 | 1
3 | 2 | 1 | 2 | Create SOP for prescription eye protection | 2015-04-30 | 1 | 1 | 1
3 | 2 | 1 | 3 | Implement driver training program | 2015-06-30 | 2 | 1 | 2
3 | 2 | 1 | 4 | Revise the hot work permit SOP | 2015-04-30 | 2 | 1 | 2
3 | 2 | 1 | 5 | Create consistent platform for tailgate safety talks | 2016-03-01 | 2 | 1 | 2
3 | 2 | 1 | 6 | Perform location safety audits | 2016-06-30 | 2 | 0 | 0
3 | 2 | 2 | 1 | Create monthly customer service topic for review in team meetings | 2015-12-01 | 10 | 1 | 10
3 | 2 | 3 | 1 | Redesign image audit template | 2015-08-01 | 3.5 | 1 | 3.5
3 | 2 | 3 | 2 | Create image audit SOP | 2015-08-30 | 3.5 | 1 | 3.5
3 | 2 | 3 | 3 | Assign committee members to locations | 2015-09-01 | 3 | 1 | 3
3 | 2 | 4 | 1 | Create a checklist to track submission thru follow up | 2016-01-30 | 2.5 | 1 | 2.5
3 | 2 | 4 | 2 | Create a sub committee for approvals and follow through | 2016-02-28 | 2.5 | 1 | 2.5
3 | 2 | 4 | 3 | Come up with standards for incentives to submit and rewards for implementation | 2016-03-30 | 2.5 | 1 | 2.5
3 | 2 | 4 | 4 | Recognize winners at monthly manager meetings & write a newsletter article | 2015-11-30 | 2.5 | 1 | 2.5
3 | 3 | 1 | 1 | Collect the data | 2015-08-01 | 5 | 1 | 5
3 | 3 | 1 | 2 | Compile the report | 2015-09-01 | 5 | 1 | 5
3 | 3 | 2 | 1 | Define criteria and standards | 2015-08-01 | 2.5 | 1 | 2.5
3 | 3 | 2 | 2 | Finalize the 2016 budget | 2016-10-31 | 2.5 | 1 | 2.5
3 | 3 | 2 | 3 | Create baselines for each location | 2016-01-15 | 2.5 | 1 | 2.5
3 | 3 | 2 | 4 | Apply to LMs incentive program | 2016-02-28 | 2.5 | 1 | 2.5
3 | 3 | 3 | 1 | Examine development and communication scores from 2015 survey | 2015-11-01 | 2.5 | 1 | 2.5
3 | 3 | 3 | 2 | Determine date of 2016 EES | 2015-12-30 | 2.5 | 1 | 2.5
3 | 3 | 3 | 3 | Set goals for these scores and compare YOY results | 2016-08-01 | 2.5 | 0 | 0
3 | 3 | 3 | 4 | Create the target for the strategic plan scorecard | 2016-08-15 | 2.5 | 0 | 0
3 | 3 | 4 | 1 | Advertise for drivers in local retirement communities | 2015-10-15 | 3.5 | 1 | 3.5
3 | 3 | 4 | 2 | Conduct cost analysis on temp vs. FT employees (Margin Committee) | 2015-11-01 | 3.5 | 1 | 3.5
3 | 3 | 4 | 3 | Determine cost of effectiveness on H-2A Visas? | 2015-11-30 | 3 | 1 | 3
3 | 3 | 5 | 1 | Launch a sub survey from the EES-12 | 2015-12-30 | 3.5 | 0 | 0
3 | 3 | 5 | 2 | Meet with 4 different focus groups (geographical) | 2016-01-15 | 3.5 | 0 | 0
3 | 3 | 5 | 3 | Examine results and create action plan for improvement | 2016-02-28 | 3 | 0 | 0
3 | 4 | 1 | 1 | Consult with Nick, Jonathan and John for action steps | 2015-12-30 | 3.5 | 1 | 3.5
3 | 4 | 1 | 2 | Set up alert for january to review course of action | 2016-01-05 | 3.5 | 1 | 3.5
3 | 4 | 1 | 3 | Organize a meeting to draft SOP and prep for launch | 2016-02-28 | 3 | 0 | 0
3 | 4 | 2 | 1 | Create a list of metrics | 2015-08-01 | 5 | 1 | 5
3 | 4 | 2 | 2 | Set up calendar alerts to schedule quarterly panel reviews for defined HPEs in 2016 | 2015-09-01 | 5 | 1 | 5
3 | 4 | 3 | 1 | Research 3 IDP designs and create one for MKC | 2015-10-10 | 3.5 | 1 | 3.5
3 | 4 | 3 | 2 | Ensure HPEs have multiple departmental experiences; create pathways | 2016-01-15 | 3.5 | 1 | 3.5
3 | 4 | 3 | 3 | Set up meeting to train LMs on how to administer, maintain and log progress on new IDP template for HPEs | 2016-02-28 | 3 | 0 | 0
3 | 4 | 4 | 1 | Prep flyers to recruit teachers and include instructions for distribution | 2016-01-20 | 5 | 0 | 0
3 | 4 | 4 | 2 | Re-advertise with retirement communities | 2016-02-01 | 5 | 1 | 5
3 | 4 | 5 | 1 | Start recruiting efforts for Cloud County 2 program | 2015-11-30 | 5 | 1 | 5
3 | 4 | 5 | 2 | Log progress and effectiveness of FLM+ Sales Training program | 2016-01-15 | 5 | 0 | 0
3 | 5 | 1 | 1 | Examine wellness requirements for new benefits package | 2016-02-01 | 5 | 1 | 5
3 | 5 | 1 | 2 | Determine new courses of action | 2016-03-01 | 5 | 1 | 5
3 | 5 | 1 | 3
4 | 1 | 1 | 1 | Prepare proforma & feasability report for outright ownership | 2015-10-01 | 4 | 1 | 4
4 | 1 | 1 | 2 | Schedule a meeting & conduct comparative analysis | 2016-01-15 | 3 | 1 | 3
4 | 1 | 1 | 3 | Determine best course of action & define new tasks | 2016-01-30 | 3 | 0 | 0
4 | 1 | 2 | 1 | Pilot tracking devices in one of each type of vehicle | 2015-10-31 | 4 | 1 | 4
4 | 1 | 2 | 2 | Purchase devices | 2015-12-01 | 3 | 1 | 3
4 | 1 | 2 | 3 | Device installation & set up | 2016-01-15 | 3 | 1 | 3
4 | 2 | 1 | 1 | Hire a manager of application development | 2015-09-05 | 10 | 1 | 10
4 | 2 | 2 | 1 | Hire a business Intelligence specialist | 2013-09-30 | 4 | 1 | 4
4 | 2 | 2 | 2 | Determine which dashboard proposals are critical | 2015-09-15 | 3 | 1 | 3
4 | 2 | 2 | 3 | Have 6-7 critical dashboards complete | 2015-12-30 | 3 | 0 | 0
4 | 3 | 1 | 1 | Ensure scorecard template is complete | 2015-06-30 | 2.5 | 1 | 2.5
4 | 3 | 1 | 2 | Determine grain quality grades | 2015-06-30 | 2.5 | 1 | 2.5
4 | 3 | 1 | 3 | Examine location's financial dashboard results | 2016-03-30 | 2.5 | 0 | 0
4 | 3 | 1 | 4 | Pilot results into new incentive program to verify feasbility | 2016-03-30 | 2.5 | 0 | 0
4 | 4 | 1 | 1 | Examine and document 5 other feed operations that are viable | 2015-10-30 | 3.5 | 1 | 3.5
4 | 4 | 1 | 2 | Determine appropriate course of action | 2015-12-30 | 3 | 0 | 0
4 | 4 | 1 | 3 | Announce new structure and create new milestones | 2016-02-28 | 3 | 0 | 0
4 | 4 | 2 | 1 | Prepare detailed outline for the BOD | 2015-11-30 | 5 | 0 | 0
4 | 4 | 2 | 2 | Post to Board Portal for review | 2015-11-30 | 5 | 0 | 0