## Perspectives
PID | Description | Progress
1 | Stakeholder | 50.8333
2 | Internal Processes | 17.2222
3 | Organizational Capacity | 30.4167
4 | Financial | 24.375

## Objectives
PID | OBJID | Description | Column1
1 | 1 | Enhance the customer experience | 86.6667
1 | 2 | Strengthen communications & relationships | 15
2 | 3 | Make it easy to do business | 20
2 | 4 | Utilize new tools & technology | 31.6667
2 | 5 | Improve key process efficiencies | 0
3 | 6 | Build the brand | 25
3 | 7 | Renew facilities & infrastructure | 65
3 | 8 | Offer new products, programs & services | 0
3 | 9 | Attract, develop & retain the best people | 31.6667
4 | 10 | Increase profitability | 15
4 | 11 | Drive out costs | 33.75

## Initiatives
OBJID | INID | Initiative | Champion | Team | DueDate | Intent | Progress
1 | 1 | Customer experience survey project | Dave Spears | Erik, Dave C., Nichole, Mandie | 2018-02-28 | Develop the process to create a survey to measure customer experience of targeted customers by pod. HR is requesting results by the end of the FY for incentive purposes. | 100
1 | 2 | Merger partner plans | Darin | C-Suite | 2018-08-01 | Continue discussions with potential cooperative merger partners & independent retailers. | 65
1 | 3 | Farmers of the future contact plan | Dave Spears | All business unit leaders, VPs of Ops, Erik | 2018-02-28 | Update the list and verify contact with the successful farmers of the future twice a year. | 30
1 | 4 | Location account communication plan | Dave Spears | Erik, Nichole, VPs of Ops, Nathan Eck, Jeff Jones | 2018-04-30 | Develop a proactive communications strategy with location accounts. | 65
2 | 1 | Fertilizer pricing plans | Kent | Troy, Matt, Doug | 2018-06-30 | Push fertilizer prices to customers. | 0
2 | 2 | "Emerging Producer" business growth tracking plan | Kent | Troy, Devin | 2018-07-30 | Determine how to best track business growth or volume in dollars with EPs. Possibly contingent upon CRM updates. | 0
2 | 3 | Landowners communication investigation | Nichole | Dave Spears, Dave C. | 2018-04-30 | Investigate & develop a method to communicate with landowners the value of the cooperative and our services through the tenant. | 30
2 | 4 | MKC Story video project | Nichole | Nathan from IT, Jeff Jones, Jeff F., Willie | 2018-05-01 | Better tell the MKC story through video. Capture the customer perspective and how we create value for them. Consider a series around the 3 legged stool and how it all fits together. Video could be used at customer meetings or in conjuction with employee trainings on our farm gate service approach. | 30
3 | 1 | Grower portal project | Matt | Nichole, All business unit leaders, Jeff Jones, Dave Sell, Tony, Devin, Mandie | 2018-05-30 | Phase 2 (website replacement)-Enhance the grower portal and establish YouTube training video. Hold training sessions for basic navigation of existing customer portal. | 0
3 | 2 | Mobile app project | Matt | Ben, Troy, Nichole, Willie, Mandie, Devin | 2018-12-31 | Research and develop a customer facing mobile app. | 30
3 | 3 | Agronomy central dispatch investigation | Erik | Matt, Jeff Jones, Doug, Nathan, Ted, Dave Sell, Anne | 2018-03-01 | Investigate central dispatch for agronomy operations. Will pilot the plan in Lindsborg and Groveland first then Manhattan will follow. Agworks version 4 is being tested now for software feasibility. Internal audits will be conducted on the work order process as well as operational efficiency decisions made after reviewing LDI's KPIs on a bi-weekly basis. | 30
4 | 1 | PA software implementation & training plan | Troy | Ross, Mandie | 2018-11-01 | Map out and execute steps for PA software implementation & training. | 30
4 | 2 | Data solution research project | Matt | Mandie, Aric, Anne | 2018-04-30 | Research a data solution for pulling data from different systems and dashboards. This is not an ALL employee forward facing application. This will be a site for IT to direct those whose job functions require data analysis to instead of making them visit multiple data points to get what they need. | 0
4 | 3 | Energy software project | Dave Sell | Mandie, Matt, Accounting | 2018-08-30 | Get approval and begin implementing new energy software. The design and software have been chosen. Project will be reviewed again in AUG. | 65
5 | 1 | Annual ERP system review | Matt | Danny | 2018-08-30 | Finalize annual plan to review processes and procedures in our ERP system. The annual plan is in place. Currently reviewing the 2017 list and implementing recommendations from RSM. | 0
5 | 2 | CRM utilization plan | Nichole & Mandie | Devin, Kent, Marketing team | 2018-08-30 | Develop a strategy for best utilizing the CRM system. This plan is still in the define and design phase. Soon it will move to Dynamics 365 (in the cloud). Timelines can change based on the upgrade strategy. Training should include data entry, dashboard tools & views, why we need contact data & cutomer purchasing habits. Consider including training refreshers via webinars in the training plan. | 0
5 | 3 | HR management software research project | Anne | Jeff F., Matt, Mandie, Erin, Chris, Ted, Erik, Hilary | 2018-08-30 | Research is underway to choose the best software that will include performance management, electronic files, goals and training. | 0
5 | 4 | Expense management software study | Chris | Matt, Mandie, Katie | 2018-12-01 | Met with RSM for potential solutions; awaiting results on recommended solutions. | 0
6 | 1 | Property upgrade & greenfield site evaluations | Jon | Erik, Ted, Dave Spears, Dave Sell, Danny | 2018-08-30 | Evaluate existing and new property upgrades to drive market growth. Include greenfield sites and bunkers. | 0
6 | 2 | MKC Direct program | Dave Spears | Doug, Troy, Kent, Willie, Nathan, Chris | 2018-05-30 | Roll out cash and carry program. | 0
6 | 3 | Employee reviews training plan | Anne | C-level executives | 2018-03-30 | Training piece for administering reviews is complete as well as the protocol for development plans. Next steps include education and formal roll out. Added structure & follow up to training request process for lessons learned. | 100
6 | 4 | High potential employee development plans | Anne | Dave Spears, Danny, Ted, Hilary, Erik, Jeff J. | 2018-08-30 | Research is underway for systems to identify employee skills and how to address them and prepare for future opportunity. | 0
7 | 1 | Custom application rig & mobile asset study | Nathan | Ops team | 2019-01-30 | Working with LDI on farm mobile PUC’s. Set up and ready for analytics. Metrics are in place. Awaiting farms to release acres to gain data. | 65
8 | 1 | Benchmarking research project | Troy | Chris, Tricia, Devin, Matt, CJ, Sara | 2018-12-30 | Benchmark (avg. price of grain by customer, avg. spend per acre + more) research project. Investigate AgSolver project. | 0
8 | 2 | Cattle risk management business plan | Devin | Dave Spears, Darin | 2018-03-30 | Rolling out the business plan for cattle risk management focusing on existing owners who are raising livestock. | 0
8 | 3 | "Emerged Producer" engagement program | Kent | Devin, Nichole, Troy, Willie, Jeff Jones, Nathan Eck | 2018-06-30 | Design and propose options to best engage with the "Emerged Producer" (those age 40-50). A field experience may be best in the summertime. Will research the Edge Program. | 0
9 | 1 | Employee turnover research project | Jeff Frizell | Erin, Anne | 2018-08-30 | Research employee turnover and develop goals to benchmark against. | 30
9 | 2 | Key employee recruitment plan | Anne | Director of Ops, Erik, Jeff F., Hilary | 2018-08-30 | Identify key roles that will become vacant in the near future and avenues to recruit and obtain quality candidates. Target key employees and facilitate ongoing relationships with a recruitment mindset. | 0
9 | 3 | Target marketing plan for seasonal PT help | Jeff | Nichole, Hilary | 2018-06-30 | Targeting and recruit pool of seasonal PT help. Advertising is active on social media and at locations. Targeting schools, specifically bus drivers. | 65
10 | 1 | Location consolidation plans | Erik | Ted, Danny, Dave Spears, Ops Team, Dave Sell, Anne | 2018-12-30 | Investigate location consolidation options and include cardtrol locations. | 0
10 | 2 | LOL agronomy operations study | Erik | Doug, Ops Managers | 2018-02-28 | Implement specific results of the LOL study as it pertains to agronomy operations. | 30
11 | 1 | Agronomy center forecasting project | Doug | Sr. Location Managers, Troy, Kent | 2018-06-01 | Monitor and evaluate success of forecasts by agronomy center and tie to an incentive plan. | 0
11 | 2 | Expense management training plan | Chris | Ops team, HR | 2018-03-01 | Training on expense management initiatives for key employees. | 65
11 | 3 | Custom application rate strategy | Dave Spears | Erik | 2018-08-30 | Rework custom application rate strategy and visit more frequently. | 0
11 | 4 | Cost of production analysis tool | Troy | Kent, Devin, Matt | 2018-03-18 | Develop a standardized method for cost of production analysis. | 70

## Tasks
OBJID | INID | TASKID | Description | DueDate | Weight | Complete | Measure
1 | 1 | 1 | Find out if we can sub out survey to LOL | 2017-12-15 | 3 | 1 | 3
1 | 1 | 2 | Launch the survey | 2018-01-15 | 3.5 | 1 | 3.5
1 | 1 | 3 | Get results to HR for incentive planning | 2018-02-28 | 3.5 | 1 | 3.5
1 | 2 | 1 | 3rd quarter follow up - update & review spreadsheet | 2017-11-01 | 3 | 1 | 3
1 | 2 | 2 | 4th quarter follow up - update & review spreadsheet | 2018-02-01 | 3.5 | 1 | 3.5
1 | 2 | 3 | 1st quarter follow up - update & review spreadsheet | 2018-05-01 | 3.5 | 0 | 0
1 | 3 | 1 | Set up a meeting to go through the customer list | 2018-01-15 | 3 | 1 | 3
1 | 3 | 2 |  |  | 3.5 | 0 | 0
1 | 3 | 3 |  |  | 3.5 | 0 | 0
1 | 4 | 1 | Assigned customer list and manual tracking method | 2017-12-15 | 3 | 1 | 3
1 | 4 | 2 | Decide on method to collect email addresses and cell phone numbers | 2018-02-28 | 3.5 | 1 | 3.5
1 | 4 | 3 | Build out campaign ideas | 2018-03-30 | 3.5 | 0 | 0
2 | 1 | 1 | Set up a meeting with champion team to discuss approach | 2017-12-30 | 3 | 0 | 0
2 | 1 | 2 | Identify which price sheet to use | 2018-01-30 | 3.5 | 0 | 0
2 | 1 | 3 | Identify which price levels | 2018-02-28 | 3.5 | 0 | 0
2 | 2 | 1 | Visit with CRM team to determine if data can be structured there | 2018-01-30 | 3 | 0 | 0
2 | 2 | 2 | Set up account contact relationships | 2018-02-28 | 3.5 | 0 | 0
2 | 2 | 3 |  |  | 3.5 | 0 | 0
2 | 3 | 1 | Follow up with Nichole on next steps | 2017-12-15 | 3 | 1 | 3
2 | 3 | 2 | Create a brochure to include value added topics specifically for landowners | 2018-02-28 | 3.5 | 0 | 0
2 | 3 | 3 | Plan for distribution | 2018-03-30 | 3.5 | 0 | 0
2 | 4 | 1 | Research production vendors | 2017-12-30 | 3 | 1 | 3
2 | 4 | 2 | Prep the shoot plan including participants and farm locations | 2018-02-28 | 3.5 | 0 | 0
2 | 4 | 3 | Begin filming | 2018-03-30 | 3.5 | 0 | 0
3 | 1 | 1 | Follow up with Matt in regards to defining the parts of phase 2 | 2018-03-01 | 3 | 0 | 0
3 | 1 | 2 |  |  | 3.5 | 0 | 0
3 | 1 | 3 |  |  | 3.5 | 0 | 0
3 | 2 | 1 | Narrow down the vendors | 2017-12-31 | 3 | 1 | 3
3 | 2 | 2 | Define the MKC part of the project | 2018-01-30 | 3.5 | 0 | 0
3 | 2 | 3 | Rollout the TMA part of the project preharvest | 2018-06-01 | 3.5 | 0 | 0
3 | 3 | 1 | Pilot central dispatch in Groveland and Lindsborg | 2018-01-30 | 3 | 1 | 3
3 | 3 | 2 | Pilot in Manhattan | 2018-02-28 | 3.5 | 0 | 0
3 | 3 | 3 | Determine software needs (testing Agworks version 4) | 2018-03-30 | 3.5 | 0 | 0
4 | 1 | 1 | Integrate GP and FieldAlytics | 2017-11-30 | 3 | 1 | 3
4 | 1 | 2 | Set up a meeting with Anne to determine formal training options | 2017-12-30 | 3.5 | 0 | 0
4 | 1 | 3 | Launch training and continue to use the data silo tool to clean up duplicates | 2018-02-28 | 3.5 | 0 | 0
4 | 2 | 1 | Define the project | 2018-02-28 | 3 | 0 | 0
4 | 2 | 2 | Follow up with Matt on next steps | 2018-03-15 | 3.5 | 0 | 0
4 | 2 | 3 |  |  | 3.5 | 0 | 0
4 | 3 | 1 | Define and design the project | 2017-11-01 | 3 | 1 | 3
4 | 3 | 2 | Select the software | 2017-12-01 | 3.5 | 1 | 3.5
4 | 3 | 3 | Revisit in AUG | 2018-08-30 | 3.5 | 0 | 0
5 | 1 | 1 | Follow up w/Danny on best review times & determine next FY items to consider | 2018-01-30 | 3 | 0 | 0
5 | 1 | 2 |  |  | 3.5 | 0 | 0
5 | 1 | 3 |  |  | 3.5 | 0 | 0
5 | 2 | 1 | Still defining and designing-move CRM to dynamics 365 (in the cloud) | 2018-01-30 | 3 | 0 | 0
5 | 2 | 2 | Prepare a training plan to teach navigation and functionality | 2018-03-30 | 3.5 | 0 | 0
5 | 2 | 3 |  |  | 3.5 | 0 | 0
5 | 3 | 1 | Follow up on specs for the scope of the project | 2018-02-28 | 3 | 0 | 0
5 | 3 | 2 | Send out RFPs | 2018-03-30 | 3.5 | 0 | 0
5 | 3 | 3 | Start demos | 2018-05-01 | 3.5 | 0 | 0
5 | 4 | 1 | Follow up after RSM visit | 2017-12-30 | 3 | 0 | 0
5 | 4 | 2 |  |  | 3.5 | 0 | 0
5 | 4 | 3 |  |  | 3.5 | 0 | 0
6 | 1 | 1 | Manhattan office remodel | 2018-06-30 | 3 | 0 | 0
6 | 1 | 2 | Storage upgrades-Benton, Burns, Lindsborg, Walton & Longford | 2018-09-30 | 3.5 | 0 | 0
6 | 1 | 3 | Agronomy terminal & seed plant investigation | 2018-12-30 | 3.5 | 0 | 0
6 | 2 | 1 |  |  | 3 | 0 | 0
6 | 2 | 2 |  |  | 3.5 | 0 | 0
6 | 2 | 3 |  |  | 3.5 | 0 | 0
6 | 3 | 1 | Design the protocol for development plans | 2018-03-30 | 3 | 1 | 3
6 | 3 | 2 | Education and formal roll out for development plans | 2018-03-30 | 3.5 | 1 | 3.5
6 | 3 | 3 | Develop how to share forward learning from training requests | 2018-03-30 | 3.5 | 1 | 3.5
6 | 4 | 1 | IT to draft the project scope | 2018-02-28 | 3 | 0 | 0
6 | 4 | 2 | Send out RFPs | 2018-03-30 | 3.5 | 0 | 0
6 | 4 | 3 | Start demos | 2018-05-01 | 3.5 | 0 | 0
7 | 1 | 1 | Install 1st round of pucks | 2017-11-30 | 3 | 1 | 3
7 | 1 | 2 | Install 2nd round of pucks | 2018-02-28 | 3.5 | 1 | 3.5
7 | 1 | 3 | Evaluate KPIs (baselines are determined) | 2018-08-30 | 3.5 | 0 | 0
8 | 1 | 1 | Decide what to benchmark by sending a survey to growers | 2018-01-30 | 3 | 0 | 0
8 | 1 | 2 | Get soil test data | 2018-02-28 | 3.5 | 0 | 0
8 | 1 | 3 | Pilot benchmarking with 5 growers to start | 2018-03-30 | 3.5 | 0 | 0
8 | 2 | 1 | Will update after TMA Planning Session | 2018-01-30 | 3 | 0 | 0
8 | 2 | 2 |  |  | 3.5 | 0 | 0
8 | 2 | 3 |  |  | 3.5 | 0 | 0
8 | 3 | 1 | Re-examine list of growers to participate | 2018-01-30 | 3 | 0 | 0
8 | 3 | 2 | Design the program content and budget | 2018-03-30 | 3.5 | 0 | 0
8 | 3 | 3 | Present the budget and look for sponsors | 2018-05-30 | 3.5 | 0 | 0
9 | 1 | 1 | Research segments of turnover | 2018-03-30 | 3 | 1 | 3
9 | 1 | 2 | Develop goals for each segment | 2018-04-30 | 3.5 | 0 | 0
9 | 1 | 3 | Review results in AUG planning session | 2018-08-30 | 3.5 | 0 | 0
9 | 2 | 1 | Identify roles that will become vacant in the near future | 2018-03-30 | 3 | 0 | 0
9 | 2 | 2 | Identify avenues to recruit and obtain talent | 2018-04-30 | 3.5 | 0 | 0
9 | 2 | 3 | Document recruitment pathways | 2018-06-30 | 3.5 | 0 | 0
9 | 3 | 1 | Advertise on social media channels | 2018-03-01 | 3 | 1 | 3
9 | 3 | 2 | Create campaign to target school bus drivers | 2018-03-30 | 3.5 | 1 | 3.5
9 | 3 | 3 | Brainstorm other recruitment options | 2018-06-30 | 3.5 | 0 | 0
10 | 1 | 1 | Evaluate all non hub fertilizer assets | 2018-06-01 | 3 | 0 | 0
10 | 1 | 2 | Analyze where additonal grain storage would allow for seasonalized options | 2018-08-01 | 3.5 | 0 | 0
10 | 1 | 3 | Examine cardtrol location activity | 2018-12-30 | 3.5 | 0 | 0
10 | 2 | 1 | Phase one - discovery | 2017-12-30 | 3 | 1 | 3
10 | 2 | 2 | Phase two - evaluate physical assets | 2018-08-01 | 3.5 | 0 | 0
10 | 2 | 3 | Determine best approach | 2018-12-30 | 3.5 | 0 | 0
11 | 1 | 1 | Set up meetings with agronomy managers | 2018-03-30 | 3 | 0 | 0
11 | 1 | 2 | Complete forecasting with all locations | 2018-05-01 | 3.5 | 0 | 0
11 | 1 | 3 | Evaluate results | 2018-08-30 | 3.5 | 0 | 0
11 | 2 | 1 | Decide what we need to train on now | 2017-11-30 | 3 | 1 | 3
11 | 2 | 2 | Develop the plan | 2017-12-30 | 3.5 | 1 | 3.5
11 | 2 | 3 | Begin training sessions | 2018-01-30 | 3.5 | 0 | 0
11 | 3 | 1 | Set up a meeting to discuss current strategy | 2018-03-30 | 3 | 0 | 0
11 | 3 | 2 | Decide on frequency of review | 2018-04-30 | 3.5 | 0 | 0
11 | 3 | 3 | Notify employee groups of any changes being made | 2018-08-30 | 3.5 | 0 | 0
11 | 4 | 1 | Calculator is built | 2017-12-31 | 3.5 | 1 | 3.5
11 | 4 | 2 | FM's trained and using it | 2018-01-30 | 3.5 | 1 | 3.5
11 | 4 | 3 | Figure out how to store the data | 2018-02-28 | 3 | 0 | 0

## Measures
OBJID | MID | Measure | Target | Actual
1 | 1 | Customer Retention | 95%
1 | 2 | Customer Satisfaction | 85% | 83%
1 | 3 | Share of Wallet | 60% | 51%
2 | 1 | Grain Quality | 0 | 0.0175
2 | 2 | Avoidable Claims | 125000 | 104533
3 | 1 | ROIC by Project | 8%
3 | 2 | Number of New Members | 225 | 186
3 | 3 | New Member Revenue | TBD
3 | 3 | Employee Turnover | 15% | 15%
4 | 1 | Return on Equity | 8% | 12.18%
4 | 2 | ROS | 2% | 4.39%